Local and Regional Action Plans for Social Inclusion

##### Version 4A

Economic Development and European Policies Directorate
City of Venice

Table of Contents:

1.	Introduction	2

1.1.	Project Aims and Objectives	2

1.2.	Project partners	2

1.3.	Policy Context	2

2.	Project Activities Undertaken	2

2.1.	Steering Group Meetings	2

2.2.	Peer Review Exchange Workshops	2

2.3.	Local  Development Groups	2

2.4.	Web Site	2

3.	Outputs	2

3.1.	Developing a methodology and framework for local and regional action plans	2

3.2.	Section One: Purpose and Rational	2

3.3.	Section Two: The context for Local and Regional Action Planning	2

Social inclusion - EU policy context	2

EU NAPs framework	2

Key policy areas  for Laps and Raps	2

3.4.	Section Three: Methodology	2

Suggested Steps for developing a Local or Regional Action Plan for Inclusion	2

Introduction – the planning cycle	2

Step 1:  Building the evidence base	2

Step 2: Stakeholder analysis	2

Step 3 Problem analysis	2

Step 4 Option analysis and strategy formulation	2

Step 5 Intervention logic – going from goals to actions	2

Step 6 Adding indicators, means of verification and setting targets	2

Step 7 Risks and assumptions	2

Step 8 Bringing it all together and achieving coherence by using an adapted logical framework	2

Step 9 Signing the Accord	2

3.5.	Section Four:Case studies	2

Introduction	2

Case study 1 - Portugal: Social Network programme	2

Case study 2 - Czech Republic: Community Planning in social services	2

Case study 3 – Finland: Vantaa School drop out project	2

Case study 4 – Ireland: Territorial employment Pacts and the Dublin TEP	2

Case study 5 – Sweden: Integration action plan in Malmo	2

Case study 6 – United Kingdom: Emda’s Economic Inclusion framework	2

Case study 7 - Czech Republic: Roma in Pezinok	2

Case study 8 – Exchange network: Cities Action to Combat Social Exclusion	2

3.6.	Section Five:Measuring the impact	2

European level	2

National and regional level	2

Problems with the common indicators	2

3.7.	Section Six:Integration into the Labour Market of Vulnerable Groups	2

Report on "Integration into the Labour Market of Vulnerable Groups"	2

Case studies	2

Section One: Projects aimed at particular groups of vulnerable people	2

Section Two: area based projects aimed at reducing concentrations of unemployment and economic inactivity	2

Section Three: Case Studies of Intermediate Labour Markets and Transitional Jobs Programme	2

3.8.	Section Seven: Conclusions and Next Steps	2

4.	ANNEXES	2

# Introduction

This report constitutes the end of year one report of the Laps and Raps project The report as such is a report of “work in progress”. The report brings together the work undertaken by the project in year one and thus creates a synthesis which enables easy access into the work of the project. The report also outlines the next steps that will be undertaken in year two of the project. The report has been produced as an “online” document and as such contains links to a wide range of documents and reports produced by the project as well as those in the public domain. The aim is to enable users to get access to information easily where their needs require.

## Project Aims and Objectives

The overall aim of the Laps and Raps is to develop a framework and methodology for the creation of Local Action Plans (Laps) or Regional Action Plans (Raps) for Social Inclusion which will enable the more effective integration of area-based approaches with wider conurbation or regional and national-level strategies.

The need for such a connection is reflected in the fact that despite the centrality of the issue of social exclusion in terms of policy, the role of cities, towns and regions in the development of National Action Plans for Social Inclusion (NAPs) has been ad hoc and somewhat marginal.

In order to achieve this overall aim the project has the following specific objectives :

- to develop and undertake four transnational peer review and development workshops. The first workshop would focus on developing a draft common framework and methodology. The three subsequent workshops would apply this methodology and focus on one of the six key policy themes of the NAPs . The peer review workshops need to be viewed as a rolling, cumulative process. The overall aim is to support the development of a common framework and methodology for developing LAPs /RAPs. The end result would be a template relating to each priority which would provide the means for each Local Development Group to develop their LAP/RAP.

- to establish at each partner location a Local Development Group(LDG). Each LDG would have cross sectoral representation and seek to have a link with the unit responsible for the development of the National NAPs. Each workshop would bring together a delegation of 3 participants from Local Development Group that each partner will establish at the outset of this project.

- to develop an online good practice exchange and development forum, which will bring together access to resources, case studies connections with practioners and policy officers for developing local, regional and National plans. The online good practice exchange would focus on the  priority policy areas selected by project partners. The aim being to pool the experience within the partnership and beyond in order to create an online resource that can be useful in disseminating good practise and the outcomes of the project,

- to assist local partners to develop/ improve local or regional plans for social inclusion.

## Project partners

The partnership brings together a diverse mix of public bodies, local authorities and NGOs from 7 EU Member States that are all involved in local/regional/national  work related to tackling social exclusion as well as working on a Europe wide level. All partners have also strong links with other agencies and organisations working with this issue.

The project is coordinated by the City of Venice (Italy) with scientific and technical support from QeC ERAN.  The full list of project partners is:

- City of Venice (Italy),

- QeC-ERAN (Belgium),

- the Association for the Development of West Athens (Greece),

- the Fondazione G. Brodolini (Italy)

- Comune di Crotone (Italy)

- the Instituto da Segurança Social (Portugal)

- Javni Zavod Socio (Slovenia)

- the Comune di Roma – Department XIV – local development, training and employment policies (Italy)

- the Municipality of Thessaloniki (Greece)

- the Ministry of Labour and Social Affairs (Czech Republic)

- the Junta de Comunidades de Castilla-La Mancha – Consejería de Trabajo y Empleo – Dirección General de Trabajo e Inmigración (Spain).

For more details on the individual partners please see Annex I .

## Policy Context

Following the introduction under Article 136 and 137 EC by the Amsterdam Treaty of the fight against social exclusion among the social policy provisions, the European Council of Lisbon in March 2000 recognised that the extent of poverty and social exclusion was unacceptable. Building a more inclusive European Union was thus considered as an essential element in achieving the Union's ten year strategic goal of sustained economic growth, more and better jobs and greater social cohesion. The Lisbon Council agreed to adopt an Open Method of Coordination in order to make a decisive impact on the eradication of poverty and social exclusion by 2010.

National Action Plans on social inclusion

The National Action Plans (NAPsincl) against poverty and social exclusion are a fundamental component of the open method of co-ordination as established in the conclusions of the Lisbon European Council.

Member States have been asked to draw up their own National Action Plans on Social inclusion. These should provide an opportunity for assessment of the strengths and weaknesses of the main policy instruments already in place in the light of the common objectives and then focus on how the Member States' policies and actions, whether at national, regional or local level, will be further strengthened so as to meet the objective set in Lisbon of making a decisive impact on the eradication of poverty and social exclusion.

Thus, while taking into account the overall national situations and existing policy framework, the National Action Plans should identify what specific and concrete changes or additions are proposed to existing policies or programmes or what new initiatives are planned in order to address identified problems and weaknesses.

National Action Plans on Social Inclusion cover a period of two years - the first plans were adopted by the Member States in June 2001. A second round of plans was submitted in 2003. A third round of Naps are now in the process of being submitted for the period 2006-2008.

Following enlargement ten new Member States submitted their first National Action Plans/inclusion in July 2004. In these plans each new member state analysed the situation in relation to poverty and social exclusion, presented the strategy, objectives and targets it had established for the two year period from mid-2004 to mid-2006 and identified the specific actions it proposed to implement in order to achieve them.

Assessment of the National Action Plans for social inclusion (NAPs/inclusion)

The European Commission carried out an assessment of the National Action Plans for social inclusion (NAPs/inclusion) that all Member States submitted in July 2003 and which was formally adopted as the Joint Report on Social Inclusion in March 2004.

In its Joint Report on Social Protection and Social Inclusion the European Commission identified six priority issues for tackling poverty and social exclusion, as reflected in the policy approaches being adopted by Member States.

The Laps and Raps project seeks to address these six priority issues for NAPS by developing a common methodology for the development of Local and Regional Action plans for social inclusion which would focus on these policy themes. The need for a such a tool is reflected in a number of key contextual factors:

- Firstly, the need for such a tool is evident in light of the evaluations of the first two rounds of Naps. The overarching policy challenge that emerges is the need for Member States to ensure that there is a strong vertical and horizontal integration of economic, employment, lifelong learning, cultural, housing, health (including safety) and social policies and that a concern with preventing and eradicating poverty and social exclusion is mainstreamed across all these policy areas. Such a functional mix is essential if an integrated and co-ordinated approach to eradicating poverty and social exclusion is to be achieved.

- Secondly, too often the mainstream programmes and initiatives of various levels of government have different goals, budgets and timetables, and are targeted towards different geographical areas. Additionally, policy measures may have unintended consequences. Sometimes, measures intended to solve certain problems work against each other or create barriers to action at lower governmental levels. The result is fragmentation of effort, reducing the potential impact of programmes and resources. Better vertical integration is required.

- Thirdly, at a horizontal level, cities, towns and regions face the challenge of co-ordinating action across very different policy field such as local employment, education and training, housing, environment, planning, transport, health, welfare and finance. Functional segregation and traditional departmental specialisms often lead to ineffective and inefficient responses. New management approaches are needed for tackling the multi-dimensional and interconnected problems which cities, towns and regions increasingly have to deal with.

- Finally and relatedly, the need is reflected in the fact that despite the centrality of the issue of social exclusion in terms of policy, the role of cities, towns and regions in the development of National Action plans for Social Inclusion (NAPs) has been ad hoc and somewhat marginal.

The six policy priority issues identified for NAPs are:

- Promoting investment in and tailoring of active labour market measures to meet the needs of those who have the greatest difficulties in accessing employment;

- Ensuring that social protection schemes are adequate and accessible for all and that they provide effective work incentives for those who can work;

- Increasing the access of the most vulnerable and those most at risk of social exclusion to decent housing, quality health and lifelong learning opportunities;

- Implementing a concerted effort to prevent early school leaving and to promote smooth transition from school to work;

- Developing a focus on eliminating poverty and social exclusion among children;

- Making a drive to reduce poverty and social exclusion of immigrants and ethnic minorities.

# Project Activities Undertaken

This section provides a brief description of the actions undertaken during the first year of the project (reporting period: 01/09/05 to 31/08/06).

## Steering Group Meetings

Each partner has a representative in the Steering Group which is responsible for the development and implementation of an agreed action plan to achieve the project goals as well as undertaking regular monitoring of progress against stated targets and outcomes. The project steering group meets on a regular basis. In the first year of project duration the Steering Group met 3 times, once at the start of the project and thereafter every six months for 2 days (coinciding with the Peer Review Exchange Workshops.). Please visit our website to access the relevant documents of the meetings (Agenda, Agreed Actions, etc).

The date and venues of the Steering Group Meetings were as follows:

- Kick off meeting: Brussels,  7-8 November 2005

- SGM 2: Prague, 8 February 2006

- SGM 3:  Rome, 3-6 May 2006

## Peer Review Exchange Workshops

One of the main objectives of the Laps and Raps project has been to develop and undertake four transnational peer review and development workshops. Each workshop brought together a delegation of 3 participants from the Local Development Group that each partner had established at the outset of the project. These LDGs are cross sectoral, and connect into regional, national and local actors and ensure involvement of participants who would bring direct experience into the exchange process.

The peer review workshops need to be viewed as a rolling, cumulative process. The overall aim is to support the development of a common framework and methodology for developing LAPs /RAPs.

First Peer Review Exchange workshop, Prague 8-11 February 06

The First Peer Review Exchange Workshop took place in Prague from 8 to 11 of February 2006 and was focused on developing a concept common framework and methodology and exchange of  experience in relation to local and regional action planning..  The methodology used in developing the common framework had three elements:

- An expert paper which presented a concept common framework for developing LAPs/RAPs

- Inputs from partners in terms of  case studies

- Identification of issues/problems that need to be addressed

See section 3 of this interim report for the common framework and case studies presented.

Second Peer Review Workshop, Rome 3-6 May 06

The second Peer Review Workshop Rome workshop took place in Rome on 3-6 May 06 and involved over 50 participants who were directly involved in ‘LAPs and RAPs’ Local Development Groups.  The theme of the workshop was “the integration of vulnerable groups into the labour market.”

The workshop format involved a combination of presentations, peer review and small group exercises.  The workshop commenced with a background presentation on the EU’s Social Inclusion strategy and the role of the project. There were presentations also from independent experts from the Commission and research organisations on best practice in developing strategies for the integration of vulnerable groups into the labour market, the thematic priority that was the focus of the workshop.

Several participants made formal presentations on the strategies being pursued in their cities or by their partnerships and the more intensive small group sessions enabled the participants to further discuss the evolving ‘LAPs and RAPs’  common framework and refine objectives for their local and regional strategies. There was much exchange of experience and views throughout the workshop with a particular emphasis on mutual learning.

As a contribution to the evidence base the Rome workshop report draws on relevant evaluations and workshop discussions to identify what good practice is in the development and implementation of projects that aim to integrate vulnerable groups into the labour market.

To access the workshop report and case studies presented at the workshop, please visit our website . See also below section 3 of this  report.

## Local  Development Groups

Another major aim of the Laps and Raps project was to establish strong connections with key actors responsible for and /or involved in the development of NAPs. Each project partner has therefore established a Local Development Group which has direct links with such actors.

The Local Development groups meet bi-monthly and provide the vehicle for the effective implementation of the agreed project actions. Furthermore, this group also identifies the three delegates who will participate in the peer review exchanges. Members of the LDG also form part of the on-line mentoring network of professionals who have considerable experience of working in the field of social inclusion. Each member has created a professional profile describing his/her main expertise and interests. A link to these profiles has been added to our website.

Overview on the compositions of the Local Development Groups:

Summary:

- 10 partner cities (2 from the new member states)

- Total of 101 participants

- Gender: 50.5 % Female and 49.5 % Male

- Sector: 26 % NGO, 35.6 % Local/regional Authorities, 12.8 % Ministries, 14.8 % Public Institutions, 9.9 % Academia

## Web Site

A Laps and Raps website has been created at the outset of the project. It contains general information on project activities, project outputs and the online good practice exchange and development forum.

The website is an important tool for disseminating good practise and the outcomes of the project to a wider audience as well as enabling project participants to maintain contact with each other and to access experience, knowledge and skills of other participants in the project.

An important part of the website is the on-line good practice exchange which brings together access to resources, case studies and connections with practioners and policy officers for developing local, regional and National plans. It focuses on the six priority policy areas and pools the experiences gained within the partnership. It mainly draws on the work undertaken in the workshops but also includes a wider mapping exercise and consists of the following components:

- Case studies from the project partners relating to the area of social inclusion

- Links to reports from the Peer Review Exchange Workshops

- Professional Profiles of members of the Local Development Groups of each of the project partners who have considerable experience of working in regeneration projects/areas and therefore are able to offer support and advice to others who are promoting Local Action Plans/regional Action Plans on Social Inclusion.

# Outputs

## Developing a methodology and framework for local and regional action plans

This is the central goal of this project. In year one a concept framework and methodology has been developed. The first version formed the basis for discussion at the Prague peer review. Subsequently, a second version was produced based on the discussion in Prague and feedback from the LDGs. This formed the basis of further discussion at the second peer review in Rome. Subsequently, a third version was produced and this formed the basis for further discussion amongst the LDGs. The version presented in this report therefore constitutes the fourth version of the document. This will be subject to further discussion, addition and refinement in year two of the project.

The methodology and framework for local and regional action planning is seen as a resource that will empower local/regional actors to develop action plans that relate to EU priorities and provide a means for feeding into Naps.

The methodology and framework has the following sections:

Section One outlines the purpose and rational for developing such a resource.

Section Two provides the policy context. The aim here is to ensure that local/regional actors are “tuned in” to the EU policy context.

Section Three introduces a nine step methodology for the development, implementation and monitoring of Laps and Raps.

Section Four provides some case studies in terms of local and regional action plans.

Section Five focuses on measuring impact. The aim is to enable local and regional actors to be aware of the range of indicators that can be used in relation to developing plans.

Section Six focuses on one of the priority themes agreed by project partners: “Access to the Labour Market for Vulnerable groups”. This reflects one of the EU priority policy issues. The Section provides an overview of the issue, case studies and suggested indicators relating specifically to this theme.

Section Seven provides some initial conclusions and outlines the key steps for year two.

## Section One: Purpose and Rational

This report sets out a methodology for developing a common methodology for the development of Local and Regional Action plans for social inclusion addressing the six priority issues for NAPS as identified by the European Commission in its Joint Report on Social Protection and Social Inclusion.

The need for such a tool is reflected in a number of key contextual factors.

Firstly, the need for such a tool is evident in light of the evaluations of the first two rounds of Naps. The overarching policy challenge that emerges is the need for Member States to ensure that there is a strong vertical and horizontal integration of economic, employment, lifelong learning, cultural, housing, health (including safety) and social policies and that a concern with preventing and eradicating poverty and social exclusion is mainstreamed across all these policy areas. Such a functional mix is essential if an integrated and co-ordinated approach to eradicating poverty and social exclusion is to be achieved.

Secondly, too often the mainstream programmes and initiatives of various levels of government have different goals, budgets and timetables, and are targeted towards different geographical areas. Additionally, policy measures may have unintended consequences. Sometimes, measures intended to solve certain problems work against each other or create barriers to action at lower governmental levels. The result is fragmentation of effort, reducing the potential impact of programmes and resources. Better vertical integration is required.

Target Group

The primary target group for this report are local and regional actors who are active in the field of poverty and social inclusion. The report, however, is also targeted at national and European actors who are directly involved in the development, monitoring and evaluation of Naps. It is hoped that the common framework and methodology will provide a means for creating better links between these different levels.

## Section Two: The context for Local and Regional Action Planning

### Social inclusion - EU policy context

Since the mid 1970`s the EU has been increasingly worried by the persistence and new forms of poverty and social exclusion. The EU Council took its first resolution approving a social action programme to combat poverty in January 1974. This was the origin of the first Poverty Programme (Poverty 1, 1975-80). This was followed by Poverty 2 (1984-89) and Poverty 3 (1989-94) Programmes.

Following the recognition under Articles 136 and 137 EC of the Amsterdam Treaty of combating social exclusion as one of the fields where the Community had an active role in supporting and complementing the activities of Member States, the Lisbon European of March 2000 agreed on the need to take steps to “make a decisive impact on the eradication of poverty by 2010”.

It also agreed that Member States should co-ordinate their policies for combating poverty and social exclusion on the basis of an open method of co-ordination combining common objectives, National Action Plans and a Community Action programme. A range of common indicators was also established: common indicators

In December 2000 the Nice European Council decided to launch the new method in the field of combating poverty and social exclusion and defined a common set of four objectives:

- To facilitate participation in employment and access to resources, rights, goods, and services for all;

- To prevent the risks of exclusion;

- To help the most vulnerable;

- To mobilise all relevant bodies.

### EU NAPs framework

National Action Plans for social inclusion (NAPs/inclusion for short) play a key role in the EU process, to the extent that they translate the common objectives into national policies, while taking into account their individual national circumstances and the particular nature of national social protection systems and social policies.

All Member States submitted their first NAPs/inclusion in June 2001. A second round of plans were produced in 2004 and a third round of plans issued in 2006 for the period 2006-8. After this they will be produced on a three yearly cycle. Details of the NAPs for all member states are available on the following link: National Reports on Strategies for Social Protection and Social Inclusion

Their preparation provided an opportunity for wide information and consultation of the most concerned stakeholders and to review the bases of the national strategies to fight poverty and social exclusion. It also represented an opportunity to develop a more strategic and integrated approach. Moreover, the information provided in the NAPs/inclusion provided a good basis for the exchange of learning and best practice across the Union.

However, it needs to be noted that this potential has not been very effectively realised in practice. Most significantly,  that despite the centrally of the issue of social exclusion in terms of urban policy, the role of cities and regions in the development of National Action plans for Social Inclusion (NAPs) has been ad hoc and somewhat marginal.

The NAPs inclusion are not widely known about or understood either by policy actors involved in inclusion, the social partners or by the target groups themselves.  The local level offers an opportunity to engage actors and beneficiaries in a serious discourse about practical action that is impossible in the rarefied atmosphere of government departments at national level.

New Member States have been involved in this process, well before the date of formal enlargement. DG EMPL and each of the Acceding Countries agreed in 2002 to initiate a bilateral co-operation process centred on the drafting of Joint Inclusion Memoranda (JIMs) with the aim of identifying the key social challenges in each country, setting out the major policies in place or envisaged and highlighting a few key policy issues for further review. The JIMs were signed jointly by the Commission and each of the 10 acceding countries on 18 December 2003. This process was designed to prepare the accession countries for their full participation in the social inclusion process, which started in mid-2004 with the submission of their first NAPs/inclusion for the period 2004-2006.

The review of the Lisbon strategy in spring 2005 posed a two-fold challenge for the work under the Open Method of Coordination (OMC) for social protection and social inclusion:

- It found a gap between the common European objectives and the policies established to address them – for the OMC, this means that the process should move beyond identifying broad principles to focus on the effectiveness of policies.

- While restating the importance of the social dimension of the strategy, it sought a concentration of policy effort on creating higher growth and more and better jobs. Thus close interaction between the social protection and social inclusion OMC, with its focus on providing a high level of social protection and social cohesion, and policies for employment and growth is required.

In response, the Commission's Communication A new framework for the open coordination of social protection and inclusion policies in the European Union (streamline) outlines three overarching challenges for policies in the social protection and inclusion fields.

(a) Promote social cohesion and equal opportunities for all through adequate, accessible, financially sustainable, adaptable and efficient social protection systems and social inclusion policies

(b) Interact closely with the Lisbon objectives on achieving greater economic growth and more and better jobs and with the EU's Sustainable Development Strategy

The interaction between the OMC and the revised Lisbon process should be a dual one – social protection and inclusion policies should support growth and employment objectives, and growth and employment policies should support social objectives.

Among the Member States, Belgium, Hungary and Finland offer clear examples of this dynamic interaction in their National Reform Programmes (NRPs), by placing social objectives at the heart of their Lisbon planning, stating that their medium-term economic and employment planning should support the future sustainability and development of their social policies.

In the fight against social exclusion, "facilitating access to employment" is at the heart of Member States strategies, even more so given the increased stress on transition to work in recent reforms. Active labour market policies and a review of tax and benefit systems are being carried out, or planned, in most Member States. Where economic and employment performances have been good, and salaries and benefits were comparatively low, as in the Baltic states, employment and inclusion policies have been integrated by linking a rise in benefit levels with a rise in minimum wages, as a means both to spread the benefits of recent growth and enhance incentives to work. A number of Member States outline in their NRPs the important role which immigration is expected to play in sustaining their labour markets in the future. However, acknowledgement of the challenge of integrating immigrants, a big issue in recent NAPs for inclusion, is not evident in the NRPs.

(c) Strengthen governance, transparency and the involvement of stakeholders in the design, implementation and monitoring of policy

One of the key policy messages emerging from work under the OMC is that policy making, and delivery, bears fruit if all actors, branches and levels of government work together. The OMC has had some impact in reinforcing this message, particularly in the social inclusion area. The implementation NAPs of the EU15 reveal a wide spread of measures to improve cooperation between central, regional and local authorities. Good governance also includes the aim of mainstreaming social inclusion concerns in public policy making (including budget setting) and stronger evaluation and monitoring. In both these areas, however progress has been limited.

A number of policy priorities have also been highlighted/reinforced for the 2007-2013 period:

- to increase labour market participation,

- modernise social protection systems,

- tackle disadvantages in education and training,

- eliminate child poverty and enhance assistance to families,

- ensure decent housing,

- improve access to quality services

- to overcome discrimination and increase the integration of people with disabilities, ethnic minorities and immigrants.

The Staff working Paper Social Inclusion in Europe 2006 also highlights the need for NAPs to take on board the issue of the concentration of multiple disadvantages in certain urban and rural communities and among some groups. The paper recommends that Member States develop integrated and co-ordinated responses to multiple disadvantages and the needs of groups at particular risk such as people with disabilities, migrants and ethnic minorities (including the Roma), homeless, ex-prisoners, addicts and isolated older people. There needs to be both improved access to mainstream provision and, where necessary, targeted measures.

Finally, three current developments emerge more strongly. These are: challenges linked to increasing immigration; rising health and insurance costs; and the need for affordable care provision for children, disabled and elderly dependants in the light of both demographic change and increasing female labour force participation.

Challenges for the future of the EU social Inclusion strategy include the need for mainstreaming – i.e., to better integrate the NAPs with national policy making, including budgetary processes, and with the revised Lisbon process; better governance – i.e., better mobilisation of actors and links between different levels (national, regional and local) of government and clearer responsibility for implementation, monitoring and evaluation; and better links between the NAPs for inclusion and the Structural Funds, in particular the European Social Fund and the European Regional Development Fund.

### Key policy areas  for Laps and Raps

As stated above, at an EU level a number of policy priorities have been identified. Of these there are five which have considerable resonance at a local/regional level:

- Employment: Promoting investment in and tailoring of active labour market measures to meet the needs of those who have the greatest difficulties in accessing employment

- Access to services:  Increasing the access of the most vulnerable and those most at risk of social exclusion to decent housing, quality health and lifelong learning opportunities

- Education to work transition; Implementing a concerted effort to prevent early school leaving and to promote smooth transition from school to work

- Children: Developing a focus on eliminating social exclusion among children

- Immigrants and ethnic minorities: Making a drive to reduce poverty and social exclusion of immigrants and ethnic minorities

These five priorities should constitute the backbone of the local and regional action plans. Particular local concerns can then be added as a sixth priority or integrated into the existing structure.  For example a concern for the digital divide could be included under the third priority: Access to services.

## Section Three: Methodology

### Suggested Steps for developing a Local or Regional Action Plan for Inclusion

### Introduction – the planning cycle

Experience of a range of strategies and action plans suggests that a number of steps need to be taken in a systematic way for Local Action Plans to be successful.  What is set out below is a comprehensive approach to developing a Local or Regional Action Plan for Inclusion.  Because of pressures in the real world it is rarely possible to pursue all stages in the detail that is needed.  Time is frequently the main enemy, because of a real or perceived need to get into the implementation stage and stop being just a talking shop.

The Planning Cycle brings together all aspects of planning into a coherent, unified process.  By planning within this structure, you will help to ensure that your plans are fully considered, well focused, resilient, practical and cost-effective. You will also ensure that you learn from any mistakes you make, and feed this back into future planning and Decision Making.

Once you have devised a plan you should evaluate whether it is likely to succeed. This evaluation may be cost or number based, or may use other analytical tools. This analysis may show that your plan may cause unwanted consequences, may cost too much, or may simply not work.  In this case you should cycle back to an earlier stage. Finally, you should feed back what you have learned with one plan into the next through a review or evaluation process

The Steps are listed below and described in more detail in the sections that follow:

- Step 1 Building the evidence base

- Step 2 Stakeholder analysis

- Step 3 Problem and option analysis

- Step 4 Option analysis and strategy formulation

- Step 5 Intervention logic – going from themes to activities

- Step 6 Adding indicators, setting targets and working out means of verification

- Step 7 Risks and assumptions

- Step 8 Bringing it all together and achieving coherence by using an adapted logical framework

- Step 9 Formal signing of the inclusion framework by all the partners

The diagram below illustrates the circular nature of the project cycle:

### Step 1:  Building the evidence base

Purpose of the step: to find evidence to find out what is happening to target groups affected by the problems

Main technique: desk research

This phase involves desk research to find out as much as possible about the nature of the problems facing the target groups that you are thinking of tackling.

Policy mapping

Identify what agencies are already doing to address the problems and map it out to look at coverage. Policy mapping needs to identify all the actions by possible stakeholders that affect the situation of target groups.  These actions may be quite tangential.  For example in a strategy to increase school staying on rates it may be important to look at private and public sector recruitment practices. Young people may be leaving because they think that qualifications will make no difference in a labour market where discrimination is not curbed.

Identify what is working and what is not working

Much delivery focuses on doing the things that have always been done.  The discussion with partners works much better if there is some externally generated evidence (for example evaluations or reviews) that inform discussion and provide an evidence base so that criticism is not seen as one person’s opinion but is firmly rooted. It is also helpful to map the level of coverage of existing actions.  Often there are good practices but they only operate for some communities or as pilot projects.  If possible the cost of different approaches should be identified.

Summary of key questions to help build the evidence base:

- What does the quantitative evidence base suggest have been the trends of the relevant target groups in relation to social exclusion in your local area or region over the past few years and beyond?

- What appears to be the nature of the social exclusion in your local area?

- How does your chosen goal represent an opportunity for tackling this form of exclusion?

- What are the barriers (or market failures) underlying these trends that are holding back the target groups in your local area or region?

- What previous policy efforts have been tried and tested?  Which did and did not work and why?

### Step 2: Stakeholder analysis

Purpose of the step: to identify who the stakeholders are and what are there interests

Techniques: desk research and analysis

Stakeholders can be defined as all those that have an interest (or stake) in an activity, project or programme – in our case the action plan. This includes intended beneficiaries, and intermediaries, winners and losers and those involved or excluded in the decision making process (DFID 2004).

Stakeholders are frequently divided into primary stakeholders who are affected by the policy – either positively or negatively and secondary stakeholders – those that have an intermediary role including delivery agencies, policy makers, and field workers. Some versions limit the number by defining some of each group as Key stakeholders otherwise the potential numbers can be limitless.

Stakeholders have different interests so it is useful to define what their involvement is with the project and how their interests differ.  By systematically analysing the stakeholders it is also possible to see whether there are any missing voices.  The exclusion of the client group is perhaps the most frequent missed voice.  It is also important to assess the capacity of different stakeholders to engage in the process.   A common failure of consultation exercises is to assume that one size fits all and fail to adapt approaches to particular groups.  For example the private sector finds very long agendas and meetings frustrating and attendance drops away.  Women are often not consulted even when the subject is highly relevant to them   Sometimes special meetings are necessary to capture the voice of a particular group.  Table 3 below sets out a format for analysing different stakeholder interests.

Table 3 Stakeholder interests for a hypothetical local employment project

| Stakeholders | Interests and how affected by the problem | Capacity and motivation to bring about change | Possible actions to address stakeholder interests |
| --- | --- | --- | --- |
| Primary stakeholders |
| Potential employers | Believe that grants may be available | Important to understand barriers and solutions | Meetings with employers to discuss incentive mechanisms |
| Local unemployed and inactive people | The direct beneficiaries who should access work as a result | Important to test whether new approaches work and to secure “buy in” of users | Focus group meetings and research to deepen understanding of barriers |
| Representative organisations of the unemployed | Their members are affected directly | Important consultees | Strategy meetings |
| Secondary stakeholders |
| Employment agencies | Threatened by criticism, looking for funding | Resistant to change | Implementation of new outreach policies |
| NGOs interested in employment creation projects | Possible implementing bodies, looking for funding | Important for future delivery of plan and policy innovations | Commission pilot projects |
| Local government | Possible implementing body | Statutory responsibility for economic and social benefit. Local knowledge but limited involvement in employment | Engage as commissioning body |
| Government ministries | Funder and policy maker | Interested in ‘what works’ but little local knowledge | Create long term funding mechanism |

### Step 3 Problem analysis

Purpose: to identify all the problems and the way that they are linked to causes and effects

Techniques: Summarise evidence from step 1 followed by stakeholder meetings and analysis (stakeholder meeting may be combined with step 4)

The LAP should include a clear outline of the nature and scale of the problem in the LAP area.   A fresh and comprehensive understanding of the existing situation and the problems that exist is essential to enabling the right solutions to be found.

Stakeholder involvement in this stage will expand the way that the problem is perceived and ensure that problems are not merely ‘agency’ views.  It is particularly important to involve the users or beneficiaries (the primary stakeholders) in problem and needs analysis.

The action plan needs to recognise that problems facing the groups are complex, intractable and inter-connected.  No simple solutions are likely to work and ‘business as usual’ approaches by existing agencies need to be challenged because it is the nature of the problems facing the groups combined with the inadequacy of social policy responses that have created the problems found today.

There are many different ways of viewing the same problem.  Depending on the perspective different solutions will be deployed.  For example in the UK over the past 30 years the consensus on the causes of poverty moved away from being the result of a ‘culture of poverty’, to being seen as being caused by economic forces acting on communities in the transition from an industrial to a service economy.  Different interpretations of the problem lead to different solutions.  Under the social pathology model policy focused on the normalisation of deviance.  With the economic model intervention has focused on helping individuals to access jobs and on making work pay. The choice between different options is assisted by research evidence.

One well established technique for working with problems in a group setting is to make a problem tree. This is a simple graphical representation of the problems, their causes and effects.

Stages in drawing up a problem tree

- List all the problems that come to mind. Problems need to be carefully identified: they should be existing problems, not possible, imagined or future ones. The problem is an existing negative situation, it is not the absence of a solution

- Identify a core problem (this may involve considerable trial and error before settling on one).

- Determine which problems are “Causes” and which are “Effects.”
Arrange in hierarchy both Causes and Effects, i.e., how do the causes relate to each other - which leads to the other, etc.

Figure 3 Example problem tree on School drop out

| Academic curriculum switches off kids |  |  | Truanting |  | CAUSES |
| --- | --- | --- | --- | --- | --- |
|  |  | HIGH DROP OUT RATES |  |  | CORE PROBLEM |
| Low literacy and numeracy levels |  |  | Youth unemployment |  | EFFECTS |

Bring evidence to the stakeholder meeting

Understanding the problem needs evidence to inform the discussion.  This evidence can be from statistics and studies that you have commissioned and collected at the start of the work in step 1.   There may be a need to commission fresh research, although the long lead times for research may make this unfeasible.  Normally it is best to commission an outside consultant or one of the partners to do a quick review of available and relevant published studies and ‘grey’ literature – reports that have not been published.

It is also useful to analyse data on the problem and to look at existing data in new ways – for example by breaking it down into small spatial units to see where the problems are concentrated geographically.  Data should also be presented to illustrate the relationships with demographic characteristics, economic circumstances and other issues that affect the target groups.

Table 4 Problem and solution table for High School drop outs

| Problems | Possible Solutions | Where is best or good practice? |
| --- | --- | --- |
| Too many young people dropping out of school at 16 because inflexible curriculum | Make curriculum more interesting | Finland – most successful education system with low drop out and high average achievement |
| Lack of teachers able to teach new curriculum | Train existing teachers and recruit new ones. | Not known |
| Many students truanting in final years and not reachable by school | Develop outreach programme and offsite provision | Not known |
| Drug and alcohol abuse is affecting students | Work on drug prevention programmes | Netherlands |
| Teenage pregnancies are making girls drop out | Better sex education, outreach provision so that girls can stay in touch during pregnancy and after | Netherlands |
| Teenage counter culture and ‘cool’ street culture do not encourage students to work hard at school | Work with role models to challenge slacker culture | Nowhere yet |

### Step 4 Option analysis and strategy formulation

Purpose:  to identify the different strategy options that may be available and then to make choices between them in order to fix on a strategy.

Techniques: Stakeholder meetings and analysis (stakeholder meeting may be combined with step 3)

Be explicit about the options available

Strategy development involves making choices between options. Even if the only counter example is the ‘do nothing’ option or retain the status quo.  It helps in drawing up the action plan to be explicit about policy options and to look for evidence based ways to select between them. However, it should be noted that the evidence-based approach is often better at rejecting options than selecting them.

A range of solutions can solve any problem.  For example reducing unemployment can be addressed by increasing the ‘employability’ of the unemployed, and/or by creating jobs for people to go into.  Often a combination of different supply side and demand side measures are needed to create long-term change.

Strategy is about deciding the particular policy mix and balance of resources that best addresses the problems in a particular area.  Sometimes less is more – concentrating resources on a few effective actions is better than spreading the jam too thinly by supporting too many under funded initiatives.  Many partnership based strategies fall into the trap of doing too much and supporting too many actions by trying to satisfy all the stakeholders.  This is a particular risk in partnerships where

The strongest partners are horizontal stakeholders that supply of services to the target groups and have a vested interest to use the action plan to lever resources.

Examine research to find out what has worked elsewhere

Because exclusion is so intractable fresh ideas are needed to tackle it. There is some truth in the adage ‘there is nothing new under the sun’ Most solutions have been tried somewhere – sometimes in other parts of Europe sometimes in the USA or the developing world.  These approaches should be examined and where appropriate adapted for use in your locality or region

### Step 5 Intervention logic – going from goals to actions

Purpose: to work on the goals, objectives, outputs and activities of the action plan and to ensure that the intervention logic connecting them is explicit and clear.

Techniques: This step is best done with the stakeholders in a facilitated meeting

The step is set out in four sections:

a) From themes to Objectives

b) From Objectives to Outputs

c) From Outputs to Activities

d) Activities

The broad theme of the action plan is probably already fixed and will be based on one of the five themes from the European level.

a) From themes to Objectives

The next stage is to define an objective that the action plan will focus on.  The Objective should be achievable over a known time period.

It will be a more limited and more specific version of the theme.   One way of thinking about the Objective is to vision the changed situation that you would wish to see at a future time.   We suggest that the plan should focus on a 5-year time horizon but you can make it longer.   The Objective may also be more specific, for example by only focusing on one target group or on one service.

|  | Theme | Examples of possible objectives |
| --- | --- | --- |
| 1 | Employment | X% of current numbers of long term unemployed and inactive people are in permanent work by 2011 |
| 2 | Access to services | Full access to primary care medical services for Y% of the Roma community by 2011 |
| 3 | Education to work transition | School drop out rates are reduced to Z% of current levels |
| 4 | Social exclusion and children | Child poverty among children of single parents is reduced by W% |
| 5 | Immigrants and ethnic minorities | Somali refugees have the same unemployment levels as the host community |

Table 6 shows some examples of possible objectives based on the five themes.

b) From Objectives to Outputs

Here we focus on what outputs need to be delivered by the action plan partnership in order to deliver the objective.   In our child poverty example the outputs could be achieved by raising of parental incomes as a result of helping single parents into work and ensuring that the tax and benefit system supports this move.  Some changes might be outside the control of the action plan partnership – for example tax changes by central government. These will be built into the plan later as assumptions and risks.

c) From Outputs to activities

The final stage moves us from outputs (what we want to achieve) to activities (how we will achieve the outputs).   This is the crucial place where incoherence can creep into plans as partners try to ensure that their projects are included as activities regardless of whether they contribute to critical outputs.   Activities that do not contribute to outputs can be excluded or revised now or later when the indicators are drawn up.

d) Defining activities

The key is to ask what activity is required to deliver each output

Working out the actions to be pursued is not entirely a top down activity.  Partners have ideas about the activities that they wish to pursue in order to meet the action plan objective. What is needed is an iterative and at times negotiated process to bring appropriate activities into the activities table while excluding those that do not make significant contributions to the objective.     An activities is set out below in table 7 below:

Table 7 Activities table

| Lead partner | Description of activity | Intended outputs | Timescale start and end | Resources |
| --- | --- | --- | --- | --- |
| Benefits office | Improving welfare to work pathways for single parents | Changes to local benefit rules to ensure that work is incentivised | Start at end of Year 1 ongoing | €400000 |
| Training organisation/ colleges | Training and coaching for young parents in basic and vocational skills | Number of training places | Year 2-5 | €200000 |
| Community based NGO | Job link organisation to place residents in jobs | One stop shop for training, advice and guidance and job placement | Up and running by end of year 1 Ongoing | €500000 Secondee from govt training agency |
| Business one stop shop | Encouraging self employment among young parents | Training programme, awareness raising, business support | Up and running by third quarter ongoing | €200000 |

### Step 6 Adding indicators, means of verification and setting targets

Purpose: to add indicators, means of verification and set realistic targets to be achieved

Techniques:  The development of indicators is a technical task carried out by analysts in close consultation with stakeholders

The next step is to attach indicators to the objective, outputs and activities.  As well as identifying the indicators the sources of data to verify that the target has been reached are also identified in the third column: means of verification

These can either be from the 18 Common indicators developed at European level and discussed above or from the tertiary indicators that you can obtain at local level and should develop in the context of the intervention logic table.

In general we would suggest using local data where available as this may have shorter time lags to publication than national data as well as being more suited to the local objectives.  Where possible it is best to adapt existing data collection systems that agencies.  However some one-off surveys carried out by research institutes or foundations may be necessary despite being expensive to implement.

Our suggestion is that for the Action plan objective and the outputs you identify indicators and means of verification.  This means that you do not need to work on indicators at the level of themes or activities.

For each indicator you should identify sources of information that enable you to verify that the Objective has been achieved or that the outputs have been delivered. The table below summarises what the indicators are trying to do.

Table 8 Summary of how to relate indicators to intervention logic

| Intervention logic | Indicators | Means of verification |
| --- | --- | --- |
| Overall theme: Superior strategic theme for the action plan (based on one of the five themes) |  |  |
| Action Plan Objective: The changed situation which the action plan is trying to bring about | How to recognise that the action plan objective has been achieved by qualitative and quantitative judgements | Sources of information to show progress towards objective |
| Outputs: Products services and other deliverables generated by the action plan partnership to deliver the objective | What kind and quality of outputs and by when will they be produced? | Sources of information and methods used to show delivery of outputs |

Table 9 below illustrates how the indicators can be build into the table using a worked example of reducing social exclusion among refugees and ethnic minorities

Table 9 Worked example of indicators for measuring reduction of social exclusion among refugees

| Intervention logic | Indicators / reference targets | Means of verification |
| --- | --- | --- |
| Overall theme from themes: e.g. Reducing social exclusion among refugees and ethnic minorities |  |  |
| Action Plan Objective: To raise the income levels of refugees by increasing their employability and helping them start enterprises | How to recognise that the action plan objective has been achieved by qualitative and quantitative judgements Refugees have higher levels of income because of higher employment and self employment | Sources of information to show progress towards objective Ideally survey data on the refugee community – but this might be too expensive - some proxy might be needed |
| Outputs: improved language skills, vocational skills, job placements, | What kind and quality of outputs and by when will they be produced? Language and vocational qualifications by refugees, Quality courses delivered, numbers placed into jobs. | Sources of information and methods used to show delivery of outputs Number of courses completed by refugees, one to one business advice sessions, Analysis of Monitoring data of employment agency and business start up agency showing job placements and enterprise starts |
| Activities language classes, training programmes, enterprise advice, incubation centre focused on refugee community | This space is used for resources, inputs and timescales (see activities table) |  |

Quantifying the indicators

Once the indicators and means of verification have been defined and agreed the next stage is to quantify the indicators and decide how much progress the plan aims to achieve.  These are the explicit quantitative or qualitative achievements to be achieved by the action plan.  They should be achievable but challenging at the same time.   There is a danger with quantified indicators, which is that they can induce ‘perverse’ behaviour.  For example in the UK in order to achieve a government target for family doctors of seeing 80% of patients within 2 days of seeking an appointment some doctors surgeries refused to allow patients to book appointments more than 2 days in advance. This was inconvenient for patients that had to work and organise appointments around a busy schedule.

In some policy areas quantified indicators can be very political.  Setting an over ambitious target and then failing to achieve it can have serious effects.

You may wish to relate the quantified indicators to ‘reference targets’ that appear in some NAPs Inclusion at national level.

Summary on indicators and methods of verification

Indicators are essential but painful.  The advantage of the indicator matrix is that it forces you to link your indicators to your intervention logic.  At the same time it allows considerable freedom to select indicators that are relevant to what you want to measure rather than those available from the 18 common indicators of the European level.

- Use as few indicators as possible – they are expensive to collect and process.

- Use a variety of indicator types and remember to measure quantitative and qualitative change – qualitative change can be more useful

- Find indicators that relate directly to the outputs and objectives, this will often mean creating local indicators rather than using the 18 from the EU common framework.

### Step 7 Risks and assumptions

Purpose: to identify the risks that may affect the action plan and the assumptions on which the plan depends

Techniques: Analysis checked in consultation with the key stakeholders

Action plans partners can only control their own behaviour.  Inevitably the action plan is at risk from other partners not delivering, from changes in the external environment including other higher levels of government making changes that worsen conditions for the target groups.  An example of an external risk would be where refugee status is changed so that social security benefits, the right to work or the right to remain in the country are weakened.  This would be a national change that would impact negatively on the position of refugees in a local community

It is possible to identify three types of risk

- Internal risks that you can control (e.g.design, management systems, performance)

- External risks others control (e.g. national legislation)

- External risks no one controls (e.g. natural disasters)

Table 10 Connecting the Assumptions to the Objectives, outputs and activities

| Intervention logic | Indicators | Means of verification | Assumptions |
| --- | --- | --- | --- |
| Overall theme: Reducing social exclusion among refugees and ethnic minorities |  |  |  |
| Action Plan Objective: To raise the income levels of refugees by increasing their employability and helping them start enterprises |  |  | Refugee status is not changed by the government – refugees are able to work and claim benefits and tax credits |
| Outputs: improved language skills, vocational skills, job placements, |  |  | Partners are able to resource activities and deliver |
| Activities language classes, training programmes, enterprise advice, incubation centre focused on refugee community |  |  | Refugees can be recruited on to courses and programmes |

Key questions to uncover the assumptions

If the partnership successfully delivers all of the activities what are the assumptions about external risks that need to be made if the outputs are to be delivered?

If the partnership successfully delivers all of the outputs what assumptions about external risks need to be made if the objective is to be delivered?

Risk management

Identifying the assumptions on which the action plan depends is a passive exercise. The next step is to identify whether some of these risks can be managed.  In risk management there are three ways of handling risk:

- Risks are transferred – this can be done by forms of insurance – so that another agency bears the risk (insuring parties against rain is a common way of dealing with bad weather in the UK)

- Risks are tolerated - if it is difficult to do anything about the risk, then it may be best to take no action – especially if the cost of action is disproportionate

- Risks are treated - usually the intention is to contain the risk at an appropriate level.

### Step 8 Bringing it all together and achieving coherence by using an adapted logical framework

Purpose: to ensure that the action plan is coherent – i.e. that the actions will lead to the outputs, the outputs will lead to the objectives and the objectives support the theme

Techniques:  This can be done either as a technical exercise or as a participative exercise with the stakeholders.

The final act is to assemble all the parts that you have been working on above and put them together in a single matrix, which is called the Logical framework.

The table below shows a Logical framework or log frame that has been adapted for use with an action plan containing a number of activities rather than for a single project.  Log frames are helpful in developing action plans that are coherent with their objectives.  However, the traditional approach can be daunting for a group that is not trained in their use.

If you have gone through all the steps above then you can combine all of it into a single log frame that looks like the one in table 11 below.

Table 11 Adapted version of Logical framework table for LAPS RAPS inclusion

| Intervention logic | Indicators | Means of verification | Assumptions |
| --- | --- | --- | --- |
| Overall theme: Superior strategic theme for the action plan (based on one of the five themes) |  |  |  |
| Action Plan Objective: The changed situation which the action plan is trying to bring about | How to recognise that the action plan objective has been achieved | Sources of information to show progress towards objective | Matters outside the action plan which must happen if the objective is to be achieved |
| Outputs: Products services and other deliverables generated by the action plan partnership | Major characteristics of the outputs | Sources of information and methods used to show delivery of outputs | Matters outside the action plan which must happen if the Outputs are to achieved |

| Title of activities to achieve the outputs | Lead partner | Brief Description of activity | Intended outputs | Timescale start and end | Resources |
| --- | --- | --- | --- | --- | --- |

Activities table

### Step 9 Signing the Accord

Purpose: to signal to the outside world that the action plan has been agreed at high level, to gain publicity

Techniques:  Hold a reception and invite the 360 degree stakeholders that have contributed to the plan

It is important that the completed plan should be signed off at the highest level by the partners involved.   This event should be high profile and include a press release and an appropriate ceremony and reception.

## Section Four:Case studies

### Introduction

There has been a range of experience of developing action planning approaches at the local and regional level. These were normally not specified in terms of social inclusion but instead had a single topic focus – for example on employment or on young people. The case studies presented here (Peter Ramsden’s report) illustrate a mixture of experiences in terms of scale of operation thematic content and Member States.

The Czech and Portuguese case studies illustrate nationally driven approaches to social service planning and community planning. Examples of action plans in Finland for school drop out, Ireland for employment, Sweden for integration of ethnic minorities, the UK for Economic Inclusion and the Czech republic for Roma accessing services illustrate different ways that the themes for Regional and Local Action Plans for social inclusion have been tackled.  The experience of these programmes illustrates what is possible with a national administration that is determined to bring its policy down to the local level. Finally the example of the Eurocities project sheds some light on how cities can network together to combat social exclusion.

### Case study 1 - Portugal: Social Network programme

The policy development process in Portugal is rather centralised and the most frequently used level of consultation is national. Partnerships between public and private institutions, at local and national level, are very common and partnership working is well established. This experience has created the conditions for the incorporation of the partnership principle in current management of social policies and increased the participation of representative national organisations in policy development. The general objectives of partnerships are to combat poverty and social exclusion and to promote local social development through the introduction of joint strategic planning dynamics. Montijo Social Network is a good example of one of the local partnerships. It is ongoing and was initiated in 2001. Its main objectives are the implementation of joint planning processes on the basis of social diagnoses, the promotion of co-ordinated intervention in municipalities and parishes, the search for solutions to problems/needs of families and persons in situations of poverty and social exclusion, the promotion of adequate coverage in terms of services and equipment in the respective municipalities and the promotion and dissemination of knowledge on the situation in the municipalities. (See  case study report)

### Case study 2 - Czech Republic: Community Planning in social services

Started in 1998, community planning is now the method that over half the municipalities in the Czech Republic use to plan their social services and will become an obligation in a new Social Services law to be introduced on January 1, 2007. The main output of the process of community planning, which is bottom-up oriented, is the intermediate plan of the development of social services, which is formed on the basis of the analysis of the region, the needs of the users and also the possibility to determine the priorities and procedures to ensure the accessibility of social services, on which basis the services are further created. The most important participants in the community planning are the users of the social services as well as the providers. Together with the contractors of the social services (municipalities and region) they all work together, through meetings and negotiations, to create an effective system of cooperation and participate in the realization of the individual specific measures, which are described in the intermediate plan of development. In order to avoid duplication of efforts, the Czech authorities believe that the community planning of social services in the Czech Republic should be a basis for the LAPS/RAPS in this country. (See  case study report)

### Case study 3 – Finland: Vantaa School drop out project

Drop out of vocational schools has been an increasing problem in Finland and Vantaa. A special project, “Haavi” (“net”) was set up to deal with this. A hands-on “case-manager” team took to the field and developed a highly individualised, early intervention approach. The project provided a devoted “mobile trouble shooting” team, two people, with a hands-on approach to drop outs. It meant engaging with teachers, parents, the youths themselves with a flexible, real-time and holistic way. Each situation was taken individually, and appropriate next steps designed, whether adjustments in the situation in the school, or other possibilities. About 100 youths were involved. In the first phase of Haavi drop out rate fell from 20% to 13%. The second phase of Haavi will address besides drop out from vocational school, also the transition from comprehensive school to vocational, to make it smoother. (See  case study report)

### Case study 4 – Ireland: Territorial employment Pacts and the Dublin TEP

89 Territorial Employment Pacts (TEPs), supported by the European Structural Funds Between 1996 and 1999, were established in several countries by local partnerships, with the aim of employment creation and access to jobs. The TEPs had mixed results. In general they did not succeed in influencing mainstream delivery and in some cases (for example in the UK and Ireland) they became more associated with running small scale pilot projects. The Pacts were most successful in the spreading of best practice around employment based approaches. The Dublin Employment Pact was a strategic alliance of key players who together aimed to encourage growth, increase employment and enhance social cohesion and inclusion in the Dublin region. It was particularly concerned with the needs of the long-term unemployed and those vulnerable in employment. Its approach was to provide a Dublin-wide context for encouraging locally-based solutions, best practice, innovation, networking and linkages and one of its main achievements was to bring together and integrate relevant organisations, agencies and government authorities to address strategic issues relating to the Dublin Region. (See  case study report).

### Case study 5 – Sweden: Integration action plan in Malmo

In 1999 Malmo developed an integration action plan targeting immigrants and ethnic minorities. It is structured with measures for Children and Youth, jobs and Employment and actions against racism and discrimination. It is organized around “goals” for each of which “actions”, “indicators” and “recommendations for the actors involved” are described. (See  case study report).

### Case study 6 – United Kingdom: Emda’s Economic Inclusion framework

Emda’s economic inclusion framework was an enterprise and employment based approach to inclusion, focused on the competencies of the UK Regional Development Agency of the East Midlands, responsible for the Regional Economic Strategy of the region. Published in 1998 the strategy focused on economic inclusion as a horizontal theme running across the programme. In this context, an Economic inclusion framework was developed and proposed a series of actions within the 5 vertical priorities of the RES: Climate for investment; Skills and learning; Enterprise and innovation; ICT; Sustainable communities. The Economic Inclusion framework operated as a single agency strategy aiming to work across Emda’s directorates.

Some important achievements were possible: the establishment of Social Enterprise East Midlands; the start up of the East Midlands Community Loan Fund lending to social enterprises and cooperatives; Enterprising communities (a bottom up approach to local economic development aimed at involving local communities in developing their own enterprise strategies). (See case study report).

### Case study 7 - Czech Republic: Roma in Pezinok

Pezinok is a small town with 22000 inhabitants and has a Roma population closer to 150. They live in an old block of flats on the edge of the town and a third of this population is represented by children. None of the adults has got even secondary school education, and nearly all adults are unemployed. The City of Pezinok has a strategy of economic integration of its Roma community by finding jobs for the Roma that would match their skill profile. The strategy includes the co-operation with the Job Centres so that information about job vacancies is provided to the unemployed among the Roma. They also involve a job creation programme that aims to create seasonal jobs for the Roma people, taking into account their lack of documentation and qualifications. Several initiatives were also taken in the field of public health: a regular medical check-up for children has been instituted; a system of regular visits by local government officials has been established to act as liaison between the Roma and other local inhabitants. (See  case study report).

### Case study 8 – Exchange network: Cities Action to Combat Social Exclusion

Eurocities set up a network called Cities action to combat social exclusion (CASE) in 2000, made up of 10 local authorities with a particular interest in social inclusion: Aarhus (Denmark), Barcelona (Spain), Bologna (Italy), Dublin (Ireland), Glasgow (UK), Lewisham (London, UK), Newcastle (UK), Rotterdam (The Netherlands), Stockholm (Sweden), and Trikala (Greece). The network aimed to find ways for cities to make a meaningful contribution to the NAPs Inclusion. The general pattern that emerged from the cases was that cities were focusing on the provision of training and employment, introducing new ways of delivering public services or additional services, through a leading role by the municipality but involving and linking public, private, voluntary and community organizations, and the targeted recipients of these services. Overall, the cases showed that when agencies, policy areas, and target populations have been clearly related to each other around a clear agenda and a clear division of roles and responsibilities, initiatives were successful. (See case study report)

## Section Five: Measuring the impact

“By creating indicators that give us evidence regarding outcomes for all young people, this pilot has naturally supported the change culture that all councils are seeking; demonstrating how cross-cutting policy development can facilitate positive outcomes.” - Nottingham City Council

Indicators enable decision makers to measure progress towards the achievement of outputs, objectives and themes. Without them we are unable to say whether a policy or action plan is working or not.

However, indicators only indicate, they are always in some ways a proxy measure of the real thing we want to understand. For example measures of income and wealth are frequently used to measure socio economic progress – the most classic measures being Gross Domestic Product (GDP) and its sister Gross national product.  But neither of these indicators comes close to describing how happy people or societies are. Both GDP and GNP are inflated by large pollution incidents or by commuting both of which to the citizen are negative experiences.

So indicators are a necessary evil but they need to be handled carefully and we should always apply a quality of life reality check to see whether the indicator really describes a situation.

Indicators can be either direct or indirect. Direct indicators are used to look at directly observable changes.  They can usually only be measured at output and activity level.  Indirect or proxy indicators are used for measuring when it is not possible to directly measure, where the time scale of direct indicators is too slow or it costs too much to collect.

### European level

A useful starting point for quality of life indicators was developed as part of the Urban Audit carried out by participating cities, contractors and academics and supported by the European Union. The Urban Audit has a direct link to the Lisbon agenda and provides useful source material for additional indicators of social exclusion. One good example is an indicator measuring the number of pensioners living alone.

For the purposes of the European Action plan on social exclusion the Social Protection Committee has adopted a set of 10 primary indicators and 8 secondary indicators in a Report On Indicators Of Poverty And Social Exclusion (2001). Such indicators should allow the Member States and the Commission to monitor progress towards the goal set by the European Council of Lisbon of making a decisive impact on the eradication of poverty by 2010, to improve the understanding of poverty and social exclusion in the European context and to identify and exchange good practice.

Primary indicators

- Low income rate after transfers with low-income threshold set at 60% of median income (with breakdowns by gender, age, most frequent activity status, household type and tenure status);

- Distribution of income (ratio of highest 20% to lowest 20% of incomes)

- Persistence of low income

- Median low income gap

- Regional cohesion

- Long term unemployment rate

- People living in jobless households

- Early school leavers not in further education or training

- Life expectancy at birth

- Self perceived health status

Secondary Indicators

- Dispersion around the 60% median low income threshold

- Low income rate anchored at a point in time

- Low income rate before (tax and social security) transfers

- Distribution of income

- Persistence of low income (based on 50% of median income)

- Long term unemployment share

- Very long term unemployment rate.

- Persons with low educational attainment

In June 2006, the Social Protection Committee adopted a new set of common indicators based on a new set of common objectives: Three overarching objectives and objectives for each of the three policy areas of social inclusion, pensions and health and long-term care.

The overarching objectives are to promote:

(a) social cohesion, equality between men and women and equal opportunities for all through adequate, accessible, financially sustainable, adaptable and efficient social protection systems and social inclusion policies;

(b) effective and mutual interaction between the Lisbon objectives of greater economic growth, more and better jobs and greater social cohesion, and with the EU's Sustainable Development Strategy;

(c) good governance, transparency and the involvement of stakeholders in the design, implementation and monitoring of policy.

The following objectives apply to the different strands of work:

A decisive impact on the eradication of poverty and social exclusion by ensuring:

(d) access for all to the resources, rights and services needed for participation in society, preventing and addressing exclusion, and fighting all forms of discrimination leading to exclusion;

(e) the active social inclusion of all, both by promoting participation in the labour market and by fighting poverty and exclusion;

(f) that social inclusion policies are well-coordinated and involve all levels of government and relevant actors, including people experiencing poverty, that they are efficient and effective and mainstreamed into all relevant public policies, including economic, budgetary, education and training policies and structural fund (notably ESF) programmes.

Adequate and sustainable pensions by ensuring:

(g) adequate retirement incomes for all and access to pensions which allow people to maintain, to a reasonable degree, their living standard after retirement, in the spirit of solidarity and fairness between and within generations;

h) the financial sustainability of public and private pension schemes, bearing in mind pressures on public finances and the ageing of populations, and in the context of the three-pronged strategy for tackling the budgetary implications of ageing, notably by: supporting longer working lives and active ageing; by balancing contributions and benefits in an appropriate and socially fair manner; and by promoting the affordability and the security of funded and private schemes;

(i) that pension systems are transparent, well adapted to the needs and aspirations of women and men and the requirements of modern societies, demographic ageing and structural change; that people receive the information they need to plan their retirement and that reforms are conducted on the basis of the broadest possible consensus.

Accessible, high-quality and sustainable healthcare and long-term care by ensuring:

(j)  access for all to adequate health and long-term care and that the need for care does not lead to poverty and financial dependency; and that inequities in access to care and in health outcomes are addressed;

(k) quality in health and long-term care and by adapting care, including developing preventive care, to the changing needs and preferences of society and individuals, notably by developing quality standards reflecting best international practice and by strengthening the responsibility of health professionals and of patients and care recipients;

(l) that adequate and high quality health and long-term care remains affordable and financially sustainable by promoting a rational use of resources, notably through appropriate incentives for users and providers, good governance and coordination between care systems and public and private institutions. Long-term sustainability and quality require the promotion of healthy and active life styles and good human resources for the care sector.

In the Lisbon European Council in March 2000, the Council invited the Commission to draw up an annual synthesis report on the basis of Structural Indicators, to become the instrument for an objective assessment of the progress made towards the Lisbon objectives, which then were adapted to focus on growth and jobs. A set of Structural Indicators has been used by the Commission to underpin its analysis in the 2006 Annual Progress Report on Lisbon to the European Council. The Structural Indicators cover the six domains of General Economic Background, Employment, Innovation and Research, Economic Reform, Social Cohesion as well as the Environment. This short list has been agreed with the Council.

A short list of 14 indicators has been developed to allow for a more concise presentation and a better assessment of achievements over time vis à vis the Lisbon agenda. In keeping with the recent streamlining of procedures in the wider context of the Lisbon strategy, it is foreseen to keep this list stable for three years with a start in 2004. They can be found on the Structural Indicators Circa site and are as follow:

General Economic Background

1. GDP per capita in PPS

2. Labour productivity

Employment

3. Employment rate

4. Employment rate of older workers

Innovation and Research

5. Youth educational attainment (20-24)

6. Gross domestic expenditure on R&D

Economic Reform

7. Comparative price levels

8. Business investment

Social Cohesion

9. At risk-of-poverty rate after social transfers

10. Long-term unemployment rate

11. Dispersion of regional employment rates

Environment

12. Greenhouse gas emissions

13. Energy intensity of the economy

14. Volume of freight transport relative to GDP

The EU Sustainable Development Strategy, adopted by the European Council in Gothenburg in June 2001, and renewed in June 2006, aims to reconcile economic development, social cohesion and protection of the environment. In order to monitor progress towards this overarching goal a set of indicators were developed, organised within 10 themes reflecting the political priorities of the Strategy, and related to subsequent political commitments:

1. Economic development

2. Poverty and social exclusion

3. Ageing society

4. Public Health

5. Climate change and energy

6. Production and consumption patterns

7. Management of natural resources

8. Transport

9. Good governance

10. Global partnership

Again at the European level, another interesting domain in which attempts in identifying effective monitoring and evaluation mechanisms have been carried out can be found in the field of immigration policies. In a report by the European Research Centre on Migration and Ethnic Relations (ERCOMER) an effort is made to draw up some indicators concerning the integration of people with an immigrant background in the EU Member States touching in particular the socio-economic, cultural and legal-political domains. The study stresses that benchmarking in integration is possible, though only in a modest way since no uniform indicators are yet available to make relevant and reliable comparisons between all Member States on the process of immigrant integration and the effectiveness of policies. Immigrant populations, policy instruments, definitions and statistics are too diverse for this. However, at a more modest scale and in specific cases it does seem possible to draw fruitful and methodologically justifiable comparisons between situations that are relatively similar.

### National and regional level

At the national level, administrations also maintain large data sets that focus for instance on exclusion. One excellent example is the UK’s Index Of Multiple Deprivation, which collapses 37 variables into six domains and is available for small spatial areas of about 1500 people.

At the local level interesting examples can be found, such as the pilot project undertook by Nottingham City Council and the think tank NEF to measure the well-being of young people in the city. The indicators used were designed to measure children curiosity (used as an indicator of children’s capacity for personal development or satisfaction with different aspects or domains of their lives such as their families, friendships, neighbourhoods and schools, as well their tendency to display characteristics of ‘pro-social’ behaviour and their favourite weekly activities.

Therefore well-being indicators are a practical way in which the ‘power of well-being’ can be used to join local services and functions to better meet people’s needs.

### Problems with the common indicators

There are a number of acknowledged problems with the common indicators:

- Missing variables:  In the first report on common indicators the Social Protection committee recognised that there were some weaknesses in their approach which largely arose because standard data sets for other data are not available across all Member States. In relation to housing they suggested that NAPs should provide quantitative data on decent housing, housing costs and homelessness as well as other precarious housing conditions.

- They also proposed to do further work on a range of other matters relevant to social exclusion such as access to services, debt, gender issues, literacy and numeracy and access to education and issues around people that live in various forms of institutions (prisons, elderly and supported housing, and children’s homes).

- Spatial and group data:  For LAPs and RAPs there is an additional problem, which is that some of the indicators are not available for regions and localities.  Very few are available at the neighbourhood level which may be a useful spatial level for some of the LAPs and RAPs Inclusion.  In addition some of the key aspects of social exclusion are about issues within the population affecting certain groups. Again the data may not be available in this disaggregated form.

The key point on indicators is that they should be chosen to measure progress in relation to the policy theme or objective that has been fixed. In this sense the most valid indicators are not necessarily for instance the 18 agreed indicators of the first Report on Indicators of Poverty and Social Exclusion but those that are developed and measured locally and directly relate to the objectives that have been fixed. The advantage of using local indicators is also that they may have little or no time lag because they can often be built on datasets that are already on line. This is a particular advantage compared to national datasets, which often have substantial time lags in publication because of the scale on which they operate.  Census data is often released up to two years after the survey and may only be carried out once in each decade.

## Section Six: Integration into the Labour Market of Vulnerable Groups

Integration into the Labour Market of Vulnerable Groups is one of the six thematic priorities identified by the EU social inclusion strategy. It has therefore been selected as one of the key issues for the LAPs and RAPs peer reviewing activity and has been the focus of a report by Professor Dann Finn and a collection of case studies from Europe and US on the subject.

### Report on "Integration into the Labour Market of Vulnerable Groups"

"Integration into the Labour Market of Vulnerable Groups" by Professor Dann Finn reports on the findings of a Peer Review Workshop held in Rome in May 2006. The report’s aim is to capitalise on the combination of practical experience and evidence findings.

It first describes the EU Social Inclusion Strategy and its Lisbon-related developments and the role of National Action Plans. It anayses the close link, stressed by policy makers throughout Europe, between unemployment, economic activity rates and social inclusion. It also provides evidence on the existing relationship between high concentrations of unemployment and ‘worklessness’ and an exacerbation of social exclusion and a whole range of social problems including poverty, ill health, youth disaffection, crime and family breakdown.

After discussing the main points from the expert contributions and the case study presentations from local partnerships in Portugal, Italy and Greece, the report consolidates some key aspects related to the integration of vulnerable groups in the labour market. In this respect, two dimensions should be considered when constructing labour market interventions: one concerns job availability, or labour demand; the other concerns the characteristics and circumstances of workless people, or labour supply. High levels of unemployment can indicate that employment creation has to be part of an effective strategy. However, there are still important barriers to the labour market for such groups, in terms of job search, ‘employability’, interaction between state benefits and work incentives, financial and transition risks and particular problems facing new immigrants. The report finally proposes some ‘lessons from the workshop’, such as the need for adopting targeted and client centred approaches, for building bridges to local employers and ensuring job search assistance within their local strategies.

### Case studies

The following case studies describe employment related services for the long term unemployed and some of the most marginalised groups highlighted in social inclusion strategies. Organised in three different sections, they reflect the diversity of interventions by national organisations and local partnerships that target either areas with high levels of unemployment and social exclusion or particular groups of vulnerable people.

### Section One: Projects aimed at particular groups of vulnerable people

The case studies described in this section are based on individual projects aimed at particular groups of vulnerable people, including the homeless, refugees, minority ethnic groups, and people with substance abuse problems.

Case Study 1 - ‘Off the Streets and into Work’, Foyers, and ‘Street League Lifestyles Development Programme’ (UK)

Off the Streets and into Work (OSW) is a registered charity constituted by a partnership of agencies which provide employment training, advice, and guidance to people who are homeless, or at risk of homelessness, across London (see: www.osw.org.uk). It aims to help homeless people move towards employability by providing a wide range of services including training in IT, and skills for the construction and hospitality industries, as well as help with basic skills, confidence building, job search and advice and guidance.

Foyers in the UK provide accommodation with opportunity for young people. By integrating training and job search, personal support and motivation with a place to live, they provide a bridge to independent living, and a chance for young people to realise their full potential. Unlike other accommodation, the Foyer requires a two-way agreement with residents, so that in exchange for accommodation and use of the Foyer services, the young person commits to working on an action plan to move towards personal and economic independence. What distinguishes foyers is the holistic approach they take to breaking the ‘no home: no job: no hope cycle’ experienced by many homeless and marginalised young people.

‘Street League’ is a homeless football team (www.streetleague.co.uk) that uses football as a simple but effective tool to engage a large pool of players (e.g. individuals from homeless and drug and alcohol backgrounds) on a regular basis who traditionally have little access to sporting activities. The project then aims to develop an individual’s ability to be ‘coached’, both on and off the football pitch, with the objective of progressing individuals through a programme of non-formal education. The aim is to engage, motivate, inspire and instil a sense of community and discipline in individuals through the power of the sporting experience.

Case study 2 – Reflex (UK)

The Equal (EU) REFLEX (Regenerating Enterprise Through Local Economic Exchange) project, based in the London Borough of Islington, implements an innovative model using the direct involvement of community groups to open up business creation processes and tackle barriers facing small and medium enterprises run by minority groups in areas of deprivation. It aims to tackle inequality and discrimination through new forms of business creation and growth. Key features of the REFLEX approach include the provision of training to enable members of the community organisations to become accredited business advisors; research to identify enterprise development in black and ethnic minority communities and other groups excluded in the labour market; development of business networks, and programmes to increase the capacity of community organisations to promote and support enterprise; and the identification and implementation of good practice.

Case study 3 – LEAP (Local Employment Access Projects) and STRIVE (Support and Training Results in Valuable Employment) (UK)

LEAP, a black-led community organisation based in a high unemployment area in North West London that had become increasingly sceptical about the local effectiveness of mainstream job search programmes adopted an innovative job preparation programme, ‘Strive’. It provides a combination of a short ‘tough love’ job preparation course and employment placement and retention service that appeared to be particularly successful in assisting poor people to both get and keep a job. The programme consists of a three-week intensive course followed by up to two years’ assistance with job search and placement. Its approach is based on four core principles: 1) No job should be seen as a ‘dead end’; 2) improve the self-confidence and self-motivation of clients and to develop the interpersonal skills values by employers; 3) participation is voluntary; 4) the programme is not for everyone: it’s not immediately appropriate for those who have significant basic skills needs, are disruptive, under the influence of drugs or alcohol.

Case study 4 – Casaworks for Families’ and SHIELDS (USA)

‘Casaworks for Families’, a demonstration project by Columbia University on Addiction and Substance Abuse, is based on growing evidence that addiction, poverty, violence and mental illness are overlapping problems that, unless tackled holistically, prevent women receiving welfare benefits from making a successful transition to employment. It is designed to achieve four goals: (a) facilitate and maintain abstinence, (b) promote work and economic independence, (c) address safety from violence for women and children, and (d) improve family functioning; it is based on a systematic assessment of ‘best practice’ The programme involves demonstration projects in 20 states selected to represent different sites in urban and rural areas, with different populations, welfare systems, and service capacities and to provide preliminary evidence of effectiveness. ‘SHIELDS for Families’ is a specific Casaworks site that serves recipients in the Compton and Watts communities in California.

### Section Two: area based projects aimed at reducing concentrations of unemployment and economic inactivity

The case studies in this section are area based projects that tackle concentrations of unemployment and economic inactivity.

Case study 5 – ‘Equal Access to Employment Strategy’ and ‘Full Employment Areas Initiative’ (UK)

In response to fragmentation in service delivery to disadvantaged groups, a Glasgow Equal Access Partnership, formed by the City Council; the health, social care, and education services; the public employment services; local development companies and voluntary organisations (see: www.easglasgow.com ) was set up. It signed up to a common vision that: “every adult in Glasgow, regardless of their age, gender, background, ethnicity, personal or health history should have the same opportunity as everyone else in the city to obtain and hold down meaningful, paid work”. The Partnership also introduced an ‘Equal Access to Employment Strategy’ (EAS) to coordinate and shape local activity, particularly to connect many of the specialised health and social care programmes with employment and training services in the city.

A rather different, more bottom-up method of linking services is the Full Employment Areas Initiative (FEAI), which involves ‘community animators’ working through social and kinship networks in deprived neighbourhoods to identify and engage people who are economically inactive, and then guiding them through the support system and hopefully into jobs.

Case Study 6 - The Ballyfermot Local Employment Service (IRL)

The Ballyfermot Partnership was one of 38 Area Based Companies established by the Irish Government in 1991, representing a new ‘bottom up’ approach to solving social problems especially those of unemployment and social exclusion. The Ballyfermot Partnership is now run by a voluntary management group whose task is to plan and implement actions to tackle disadvantage, poverty and increase the social and economic reputation of the community. It delivers a wide range of community development and education programmes, including the provision of child care places and measures to improve school retention rates. The Partnership attracts and has to work with a diverse range of funding sources as well as places considerable emphasis on using research and information to target its interventions effectively.

Case Study 7 - Nottingham Works (UK)

The ‘Nottingham Works’ initiative, based on a city-wide jobs partnership, aims to match the recruitment needs of local employers with unemployed and workless residents in those areas of Notthingham with high concentrations of disadvantage by ensuring that ‘local people got local jobs’. The programmes underpinning the initiative are based on a close and detailed understanding of the evolving needs of the local economy and they are the outcome of a constructive partnership between several different groups and interests, including the City Council, local employers, staff in statutory agencies, training providers and the unemployed themselves. The aspirations and the anxieties of the unemployed are taken seriously, and each individual is the focus of encouragement and support. The service is decentralised to local communities, supported through outreach, and in some centres multi lingual support was available.

Case Study 8 - The Milwaukee Jobs Initiative and the Wisconsin Regional Training Partnership (USA)

The Wisconsin Regional Training Partnership (WRTP) is one of the ‘Jobs Initiative’ projects delivered largely by the Wisconsin Regional Training Partnership in inner city Milwaukee, one of the USA’s most segregated cities. The WRTP is a non-profit association of 125 employers and unions responsible for placing hundreds of inner-city minority workers into family-supporting jobs in manufacturing. Its purpose is to help local companies modernise plants and adopt new workplace practices; to upgrade the skills of current workers; and to recruit, train, and mentor new (largely minority) employees. The WRTP developed a nationally recognized model of employment-linked training and it is currently replicating this model in new employment sectors including hospitality, healthcare, telecommunications and utilities.

WRTP plays the lead role in delivering the Milwaukee Jobs Initiative (MJI) that brings together business leaders, trade unions and community organisations to match inner city workers with good jobs.

### Section Three: Case Studies of Intermediate Labour Markets and Transitional Jobs Programme

This section contains case studies of innovative temporary job creation programmes, including a number of European Intermediate Labour Programmes (based on providing temporary wage based employment for the long term unemployed and combining periods of paid work experience with additional support and job placement services aimed at getting participants into regular jobs) and what are termed ‘Transitional Jobs Programmes’ from the USA.

Case Study 9 - The Wise Group of Companies (UK)

The Wise Group, founded in Glasgow in 1983, pioneered the concept of the ILM through combining a variety of grants and contracts that enabled it to provide temporary jobs that paid wages to the long term unemployed in a regular work environment. The organisation has since developed an international reputation for delivering innovative temporary work programmes which recruit the long term unemployed to carry out work of significant community benefit. It now runs a number of programmes through its constituent companies. The people services comprise fast track personal development and job search, call centre, care and job coaching, administration, catering services, child-care and classroom assistants, education and awareness raising, and customised training for employers.

Case Study 10 - Community and Environmental Employment (CEE) (UK)

CEE is delivered by the ‘Employment and Regeneration Partnership’, a ‘not for profit’ organisation in Manchester (www.erpartnership.com/links.aspx ), accessing and delivering government and EU funded programmes to improve the local economy, create jobs and provide skills and employment for local people. ERP implements CEE projects through a range of over local sponsoring employers and creates a pool of temporary, waged employment opportunities in areas of socially and environmental useful work. It also provides vocational training with a programme of non-vocational personal development (for example, driving lessons) as well as guidance and counselling together with job search to enable people to obtain employment in the regular labour market.

Case Study 11 - Maatwerk Amsterdam (NL)

Maatwerk Amsterdam (www.maatwerk.amsterdam.nl) is an independent ‘not for profit’ company established by the Amsterdam Municipality to deliver job creation programmes. The organisation sees its primary role as using subsidised work experience to improve individual human capital and help participants to get regular jobs. Most of its participants are young unemployed people, many of whom are from minority ethnic backgrounds. The company operates a diverse range of projects, some with the private sector, which provide real workplace discipline, support with both basic and hard skills, and the support of workplace supervisors and an individual case manager.

Case Study 12 - Vitamine W Antwerp (NL)

Vitamine W is a non-governmental organisation in Antwerp that works for people who are threatened with exclusion from the labour market (see www.vitamine-w.be).  The organisation believes that even when a person cannot be placed in regular employment a suitable activity can be found or created for every individual, if necessary outside the traditional scope of a full-time job with a permanent contract. Vitamine W activities are directed towards at-risk groups who have a hard time finding and keeping employment. Its programmes aim to improve the employability of low-skilled workers, immigrants, and the long term unemployed. Vitamine W projects also try to bridge the gap between supply and demand on the labour market and they support and advise companies and employers that work with those at-risk.

Case Study 13 - The Transitional Work Corporation in Philapelphia (USA)

The Transitional Work Corporation, founded to deliver the ‘Philadelphia@Work’ transitional jobs (TJ) programme (www.transitionalwork.org), is aimed at city welfare recipients, largely African American women with dependent children, at the point of losing their entitlement to cash benefit payments (in the state of Pennsylvania ‘TANF’ recipients must be working from two years after they first start receiving cash benefits and they lose all entitlement to cash assistance after five years). The programme supports welfare recipients moving into stable unsubsidised jobs: it provides intensive orientation for two weeks and then places each participant into transitional work that matches individual aptitudes and develops work related skills. Participation is optional. Participants work for 25 hours per week for up to six months in jobs in city government and non-profit agencies and are paid the state minimum wage. The programme aims to create a realistic work environment and participants are treated as employees.

Case Study 14 - Transitional Jobs Programmes in New York City (USA)

The Neighbourhood Work Project: Center for Employment Opportunities (CEO) provides job preparation and placement services for ex-offenders and others under community supervision in NYC (www.ceoworks.org). CEO has developed a distinctive transitional jobs approach: at the beginning it offers immediate, short-term paid employment opportunities through a day-labour programme providing maintenance and repair services to public agencies. While employed in NWP, participants meet with their employment specialists weekly to continue work on interviewing skills, follow up on job leads developed by employment specialists, and address needs that might impede their employment success, such as obtaining housing, medical services, child care or work-related documents.

EarnFair is a demonstration project that tests new ideas to improve job prospects for disadvantaged workers. It employs welfare recipients and others from job placement programmes in the city and operates in approximately the same way as a for-profit staffing agency, and workers compete in the labour market for placements in various businesses and non-profit organisations. It provides an array of employment assistance and retention services and aims to equip participants to be able to retain employment and increase their earnings.

## Section Seven: Conclusions and Next Steps

A number of initial conclusions/reflections have emerged during the first year of the project:

- Local and Regional authorities deliver many of the services on which the poor and socially excluded rely and are therefore well placed to coordinate and develop local action plans for social inclusion. Which types of services are the competences of local government or other agencies varies widely across the Member States.

- The involvement of local regional actors in the development of Naps has been very different in the 6 member states represented in the project. There is a need to strengthen EU guidelines in respect of mobilisation and involvement of actors in the development and monitoring of Naps.

- Relatedly, there is a lack of awareness at local/regional level in respect of EU policy in relation to social inclusion. Furthermore, the relationship between the EU social Inclusion policy and the EU wider Lisbon strategy is not clear for local/regional actors. There is a need to build up capacity and competence in this aspect.

- At a local /regional level the overwhelming tendency has been the development of  programme-based approaches that focus on social exclusion by  creating  a new set of initiatives supported through short term project funding. These can be seen in both domestic and EU programmes including initiatives such as Urban and Equal. Such project based approaches can bring temporary relief but rarely change the underlying factors that lead to exclusion, or the behaviours of delivery bodies that perpetuate it.

- Experience of implementation of the first two rounds of National Action Plans (NAPs) Inclusion has demonstrated that strong vertical and horizontal integration of economic, employment, lifelong learning, cultural, housing, health and social policies is needed to make progress in eradicating social exclusion and poverty.  At local and regional level there is a recognition that policy delivery is shared between a wide range of agencies and that only through better coordination and mainstreaming can improvements be made.

In terms of next steps, project partners have agreed the following actions for year two:

- To focus on the specific themes of “Integration of Immigrants” and “Access to services for vulnerable groups”, in subsequent peer review workshops.

- To review and further develop  the common framework and methodology via the LDGs

- To customise the policy section of the common framework in order to incorporate a national dimension in relation to Naps, thus providing LDG members with relevant connection to their specific context.

- To undertake local dissemination of the common methodology

- To undertake EU level dissemination of the common methodology.

# ANNEXES

Laps and Raps Project Partners

Lead partner:

Name of Organisation: 	City of Venice 
Representative: 	 	Andrea Del Mercato

Contact details: 
Economic Development and European Policies Directorate
City of Venice 
Riva del Vin 1098 
30122 Venezia 
Phone: +39 041 27 00 811 dir 824
Fax: +39 041 27 00 890 
international.relations@comune.venezia.it
www.comune.venezia.it

Short presentation of the organisation:

The City of Venice, within its own functions exercises administrative actions and manages the services, the activities and the procedures concerning: culture, social welfare, sport, tourism, environment, civil protection, commerce, local rates, public and private building, education.

It promotes, according to the principles of democracy, participation, transparency, solidarity and programming; it promotes sustainable development and the quality of life of its citizens, acting as a guarantor of person, family, pluralism, pacific cohabitation and differences of sex, race, language and religion values.

Through the twinning relationships with other national and international municipalities, it also gives great relevance to the promotion of peace policies and co-operation for the economic, social and democratic development.

The Economic Development and European Policies Directorate promotes local economic development, programs re-qualification intervention in specific areas of the city and manages all European projects and international relations of the City of Venice with foreign partners, Cities and Bodies.

The Directorate is divided in three main areas of action:

- Economic Development: promotes, coordinates and manages projects funded by national instruments for economic local development

- Competitiveness and Employment: p romotes, coordinates and manages projects funded by European instruments for local development

- Territorial Cooperation: p romotes, coordinates and manages transnational projects funded by European Union, participate in international and European network activities, disseminate information about EU activities, organise events related to projects and / or strategic themes of the City policy.

The two last areas offer technical support to the departments of the City in planning and managing European projects and in creating local and international partnerships, manage the relations with the European Commission and promote information related to EU opportunities for funding. The Directorate has a wide experience in managing EU funded projects and has a young, well-trained and highly skilled multilingual and multidisciplinary staff.

Other Areas of interest:

The City of Venice acts at European level (in agreement with Regional and central governments when required) by promoting initiatives and projects in priority areas for the growth of our Administration and of our local community:

- urban regeneration

- social policies

- culture and intercultural dialogue

- human rights

- environment and local sustainable development

The dialogue with the European Commission and the European Parliament enables our Administration and our City to build up and foster daily relations of cooperation with other cities both in and outside Europe, learning from the experience of others and firmly strengthening the process of building a united, plural and democratic Europe. From this point of view particular importance is attached to contacts with cities in South-Eastern Europe, the Mediterranean and Asia, to which Venice is naturally and historically close.

The City of Venice also acts as an active partner in decentralised cooperation programmes, taking part in European Union and United Nations schemes in support of human development (founded on the growth of the civil, political, social and economic rights of women and men) and the sustainable development of the worldâ€™s local communities in developing countries.

Name of Organisation: QeC-European Regeneration Areas Network 
Representative: 	Haroon Saad, Director

Contact details:

Rue Vieu Marché au Grains 48, B-1000 Brussels 
Belgium 
Tel: +32 (0)2 524 45 45, 
Fax: +32 (0)2 524 44 31, 
E-mail: info@qec.skynet.be

Description of on-going projects relevant to the Laps/Raps project partnership: 

QeC-ERAN is involved in a number of initiatives that relate to the issue of social inclusion:

- Gender Equality: Within the EU Gender Equality Framework the network has developed a project that focuses on the identification and development of good practise of the social and economic needs of women in area's of high need.

- Social Exclusion: Within the Urbact programme Qec- ERAN has developed and now provides the technical and professional input in relation to the Urban Diversity and Inclusion Exchange (UDIEX)

- Regeneration: Within the Interreg IIIC programme Qec-ERAN has developed with other partners a project called IMAGE . This focuses on an exchange of experience in relation to local strategies which aim to "turn around" areas that are clusters of "negativity" in terms of human, social and environmental capital

- Youth Development: Within the Ecos-Ouverture programme the network has developed and co-ordinated a project focussing on the issue of youth unemployment and in particular the transition from school to work for young people with low or no qualifications.

Name of Organisation: 	 Association for the Development of West Athens (ASDA)

Representative: 	Bitounis Panagiotis, President of ASDA

Contact details:

Ethnikis Antistasseos 65 
Peristeri 121 34 Hellas 
Tel. + 30 210 5745 826
Fax. + 30 210 57 59 547
Website: www.asda.gr, 
E-mail: mpd@asda.gr , 
gbouritis@asda.gr 
natasa@asda.gr or akatopodis@mail.asda.gr

Background

The nine municipalities of West Athens, reckoning the fact that the rapid changes occurring nowadays lead to the formation of new conditions, relations and concepts, decided to create ASDA the Association for the Development of West Athens, in 1989.During the past 16 years, ASDA has been in constant co-operation with numerous partners, both European and national, in our dynamic involvement process of West Athens.

ASDA is governed by the 47-member Administrative Council, all of them elected by the Municipal Councils of the 9 Municipalities of West Athens. The Administrative council is chaired by a 5-member Executive Committee.

ASDA has been brought into existence by the initiative of ten municipalities of the West region of Athens. Ever since ASDA has been focusing on issues of social integration, urban planning reformation elaborating studies and projects towards this direction.

Description of on-going projects relevant to the Laps/Raps project partnership:

The ASDA European projects office has taken full advantage of every given opportunity for fighting social exclusion and the marginalization of a significant part of the area population whose origin, gender, social conditions and special needs make their smooth integration into society difficult. Such opportunities are:The European Social Fund programmes, the European Initiatives HORIZON/IRIDE, INTEGRA/PREPATRE and the Social Exclusion operational programs such as ESTIA. (URBACT ECO FIN NET, URBACT UDIEX ALEP, URBACT CITIZ@MOVE EUROPE DIRECT)

Hundreds of West Athens citizens threatened with social exclusion (Repatriated Greeks, unemployed women, gypsies, juvenile delinquents, single parents etc) have either been trained, have obtained professional expertise or have been integrated into the labor market. At the same time, support structures were created, continuing to provide socio - psychological support and counseling, registering and monitoring the local market needs, counseling on how to find job and legal support in matters that involve social inclusion.

ASDA has implemented 22 training programs for unemployed or threatened by unemployment young people, co-financed by the European Union. The aim of the majority of those programmes was to familiarize young people with new technologies. 834 young men and women have been trained in total. The total expenditure was almost 1.5 million Euros.

West Athens Territorial Employment Pact

This is the result of a long-term strategy and relies on the co-operation between all the actors involved (ASDA, West Athens municipalities, Chamber of Commerce, Athens Labor Center) to promote employment. Such a strategy includes:

- Funding for the creation of new business by simplifying the processes for the provision of licenses and funding access. 1.498 new businesses were established in 1999-2000

- Funding of the enterprises that employed unemployed people (20 euros / per day / per employee). 2.585 enterprises were funded in 1999-2000

- Creation of new jobs in the social field for actions such as Supplementary support for children, elderly and disabled people, access to health and care services. 374 were trained in total. 151 of them were employed

Fighting against women's unemployment

Under the framework of the European Initiative "NOW", ASDA in close collaboration with the West Athens municipalities, has established the " New Opportunities Support Center for Women in West Athens (KNEYGDA)". It's aim was to create a permanent infrastructure in local level, for the promotion of employment and vocational training of West Athens women.

The European Initiative AVANZA 1998 - 2000 has been successor of NOW. It constitutes an integrated intervention for women's employment in West Athens, reinforcing women's entrepreneurship through the exploitation of the legal, social economic environment for designing and innovative women's enterprises.

Other Areas of interest:

ASDA European projects office has taken full advantage of every given opportunity for fighting social exclusion and the marginalization of a significant part of the area population whose origin, gender, social conditions and special needs hinder their smooth integration to the society.

Name of Organisation: FONDAZIONE GIACOMO BRODOLINI

Representative: ENZO BARTOCCI (LEGAL REPRESENTATIVE)

Contact details:

VIA A. DEPRETIS 65 - 00184 ROMA
TEL: + 39 (0)6 4746552
FAX: + 39(0)6 4746345
E MAIL: PROGETTI@FONDAZIONEBRODOLINI.IT
WEBSITE: WWW.FONDAZIONEBRODOLINI.IT

Background

The Giacomo Brodolini Foundation was established in April 1971 in memory of the ex-minister of Labour, Giacomo Brodolini, responsible for approving the Statute of Workers, still a reference point for the protection of workers rights in Italy.

The Foundation works mainly in the field of labour related research and cultural promotion given that jobs are essential for achieving social inclusion, encouraging integration, the participation of individuals in current events and contributing to the growth and enhancement of the dignity of men and women.

In line with these objectives the Foundation's expertise lies in the areas of employment, job protection and social insurance, in which it works with the most qualified experts in the field, as well as trade unionists and industry representatives, following a rigorous methodological and interdisciplinary approach.

The Foundation is based in Rome and Milan. This enables the Foundation to share in the cultural life of two of Italyâ€™s most interesting cultural places and readily to take in the formation of new cultural and scientific trends.

The Foundation's Board of Directors is composed by leading professionals from Italian Universities, trade unions and companies. Among its members there are union representatives from Italyâ€™s three national trade unions ( CGIL, CISL and UIL), representatives from the ACLIs (Italian Workers' Catholic Associations), and from the main Italian Universities.

Description of on-going projects relevant to the current project partnership:

Dynamo - Dynamics of national employment models (2004 - 2006 ) 
Funded by European Commission, DG Employment, Social Affairs and Equal Opportunities.

The project, financed by the 6th Framework Programme, has two main objectives:

- Study of European socio-economic development models;

- Analysis of possibilities to reconcile the increase in economic competitiveness and innovation with the objectives of social cohesion.

The great influence of employment trends in Europe on competition and social cohesion objectives is highlighted by the growing importance of human resources and the value attributed to greater employment opportunities.

Working group G on open learning environment, active citizenship, social inclusion and equal opportunities (2003 - 2004)

Funded by European Commission, DG Education and Culture Lifelong Learning Policy Development Unit.

Consultancy and technical assistance for European Commission social policies on learning environment, active citizenship, social inclusion and equal opportunities.

Galca - Gender analyses and long term care assistance (2002 - 2004)
Funded by European Commission, DG Employment, Social Affairs and Equal Opportunities.

An important aspect in reconciling professional and personal life is care for the elderly. Women play a key role in both unpaid family care as well as paid care work. The project aimed at identifying the long-term care services available on the basis of the interdependence between financing and care work offer. The project thus assessed the basic structure of the long-term care models that need to be adopted. At the same time the project provided an inventory of good practices, evaluating the employment potentiality of each option.

ALE - Acting Locally for Employment (2000)

Funded by European Commission, DG Employment, Social Affairs and Equal Opportunities.

The project aimed at analysing how companies (and company associations) encouraged employment by means of partnerships with local authorities.

Prospects for a lifelong learning system: current offer, changes required and efficient evaluation method for policies aimed at the adult and elderly population (2005-2006), in partnership with SPI 
The aim of the project is to provide a quantitative and qualitative description of the training offer directed at adult and elderly persons, evaluating its objectives, resources and outcomes. The research will investigate how the training system contributes to supporting not only employability but also inclusion, social cohesion and active citizenship, through the involvement of persons in the labour market at risk from social marginalisation. To this end, the level of involvement of the weakest classes in the training system will be investigated: the long term unemployed, women, the disabled, immigrants, low level qualified persons or persons in low level qualified jobs. The research will be carried out on a national basis and will be compared with similar studies carried out at European level.

Local Welfare Models (2003), in partnership with SPI 
The aim of this research was the definition of potential local welfare models that could guarantee the self sufficiency of elderly persons, in order to respond to the growing interest over the last few years of Italian Regions and other local authorities for measures to promote a wider benefit system for the non self sufficient elderly. In the identification of local welfare models the research has also looked at the difficulties in reforming this area, which requires greater resources in a period in which the Italian system is in crisis in terms of international competitiveness. 

Illegal Work Of Carers for elderly people in Italy and Europe: Practice and Policy (2002),in partnership with SPI CGIL : The research is devoted to the work of paid carers offering assistance at home to non-self sufficient elderly people. This phenomenon raises several questions and poses complicated problems for those who are involved.

Assistance to elderly people in Italy and in Europe: towards building-up a social market for services (2001 ), in partnership with SPI - CGIL The research is based on the need for: a) in-depth knowledge of financial and organizational criteria used in current European innovative measures; b) a knowledge of their impact both on welfare expenditure and on the needs of the elderly people who benefited from them; c) policy and programming indications for Italy based on the analysis of the current situation and of existing experimentation.

Other Areas of interest:

Over the last thirty years the Foundation dealt mainly with work-related matters in the following areas: work economics and sociology; labour law; industrial relations; history of trade unions and labour movement; history of the welfare state as social protection of workers and the weakest elements of our society.

The Foundation dealt with all the issues of the debate grown within the socio-economic research (especially on labour market). Such issues are a consequence of the planning policy and of the studies on flexibility and on atypical job. Due to the changing of Italian and European society, the Foundation dealt particularly with "social exclusion", inclusion, and social policy. The Foundation thinks that the struggle against social exclusion and poverty is one of the most important elements for economic and employment development. Such issues are related to the more general issue of rights, and to that of labour rights in particular.

With regard to Italian labour law, the Foundation carries out studies and research for a comment upon the workers' statute. All this is the most important political legacy Giacomo Brodolini handed on to us. In order to safeguard its meaning, it must be adjusted to the changing reality of the difficult passage to a post-industrial society requiring more mobility and flexibility along with a new, different system for subordinate job.

With regard to the system of industrial relations, the Foundation's research joined the trends in economic and productive changes to the trends in labour relations in order to understand how the change works and to point out the trends in this crucial field.

From a historiographic pointof view, scientific production mainly focused on the development of the labour movement and on the trade union organization as expression of the working class economic and professional concerns. Studies aimed at focusing on the trade union's relations with politics and on the relationship between the trade union's activities and the activities of the working class's political parties within industrial society.

The Brodolini Foundation promotes a large number of projects on the above mentioned themes funded by the European Commission (DG Employment and Social Affairs, DG Research, DG Education), which are carried out in partnership with universities, research centres, NGOs, public entities and local bodies from most EU countries.

The Brodolini Foundation cooperates with the European Trade Union Institute (ETUI) and is part of the international research networks RLDWL, Regional and Local Development of Work and Labour and

IWPLMS, International Working Party on Labour Market Segmentation.

From 2000 the Brodolini Foundation provides technical assistance to the European Commission DG Employment and Social Affairs regarding the evaluation of the Italian Employment NAP, as Italian member of the Sysdem network of the European Employment Observatory (EEO).

Name of Organisation:  Comune di Crotone

Representative: Sindaco: Armando Riganello

Contact details:

Piazza della Resistenza 
Tel e fax 0962 921418 
E-mail: valeriofrancesco@comune.crotone.it
Website: www.comune.crotone.it

Short presentation of the organisation:

Competencies : Social Policy

Policy priorites :this department promotes initiatives to help the following target group: minors, over65s, financial disadvantaged, disabled and to create better conditions in slums.

Policy team: 2 Sociologists-1 Psycologist-2 Social workers-2 Administrators

Activities :social segretariat-planning and managing initiatives. This office works as a supporter to local government body.

Provisional report ( year 2005:Social Service-Nursery- Sport- Tourism and Entertainment.

Social Service

The local authority is very interested in improving life conditions of the citizens through different and specific initiatives, aimed to the preventions of uneasy situations by means of ministerial or regional financing or by authority's own.

Minors

The project "Social Aggregation Centre" is on-going. It was organized within the Three years Plan by the Social Service based on L. 285/97( Turco law)-financial period 2000- aimed towards childhood and adolescence.

The activities are:

toy library, photos, theatre, ceramic, music, informatics laboratories, school support. The toy library and the school support activities are managed in the Don Milani School by 9 experienced operators through a collaboration contracts between the Authority and the operators. Again, there are some other activities going on:

a)        Interventions towards minors with the purpose to bring them back to their origin families;

b)       Interventions towards the minors involved in dangerous situations to help them by means of different courses ( informatic, estetic,jewel laboratories);

c)        Institution of a aggregation centre for disabled.

Moreover, to avoid conditions for marginalisation, some interventions of socialization in particular districts of the town, are on-going.

Disabled

The great number of disabled persons resulted in the launching of a series of activities to create aggregation conditions such as Informatic Music Theatre Art

The course is developing in via C. Alvaro. Besides, it is necessary to promote actions towards disabled between 3-21(funds from 162/98 L.), 6-64 ( funds 104/92 L.) It is foreseen, also, a minibus for the transport of the disabled. At the end, the local Authority has foreseen an assistance service at home

Drugs

We are going to start a project financed by Region ( L. 45/99).

Over 65s

It is foreseen(L. 328/2000):

- Assistance at home;

- Improvement of the meeting centres;

- Cultural activities involving local associations ;

- accommodation in healthy places for 100 over 65s in financial disadvantage

- assistance for bedridden patients

- Economic assistance and first ai d

It is foreseen:

Special contribution for unemployed  and financial disadvantaged people because there are a lot in the town.

Soup kitchen ( Caritas Diocesana is involved in)

Improvement of placing minors in foster care (consequently it is necessary to appoint another social worker. The action should be paid by Regional Funds.

Adoption

Creation of a specific office which takes care of national and international adoptions

Extracommunitaries

To aid the process of integration it needs to foresee : social integration and economic assistance.

This authority is going on with the project "Hotel Africa" that has got the aim to give hospitality to persons that are regular, but without means to live.

To make better the specified activities it is necessary to improve the staff and support them with a qualified technicians in the different sectors.

This department is organized a Seminar to divulgate the results of the project called "Sport ,diabete e terza età" activate in colllaboration with ASL n°5 of Crotone.

Description of on-going projects relevant to the current project partnership:

1) Aggregation social Centre n°1:

a) School support

b) Toy library

2) Training course for disadvantaged minors and micro-criminality

Objectives and finalities: to promote better life conditions from the different points of views: economic- social etc. with particular attention to people aged between the childhood and adolescence.

3) Deinstitutionalisation

This action is for the families that have not the means to keep their children.

4) Assistance at home for over 65s and disabled

Other Areas of interest:

The most important area of interest is the promotion of opportunities to live better and better through:

1)        Urban and social qualification

2)        National and international

3)        Social tourism

4)        Immigration

Name of Organisation: 	Instituto da Segurança Social, I.P - ISS, I.P

Representative: 	Edmundo Martinho 
Institute of Social Security - President

Contact details

Rua Rosa Araujo, n° 43
1250-194 LISBOA 
Portugal 
Tel. (+ 351) 213 102 000
Fax. (+ 351) 213 102 090 
Email. mailto:Edmundo.Martinho@seg-social.pt
Website: www.seg-social.pt

Background
The Instituto da Segurança Social (ISS) is the public institution of the Ministry of Social Security, Family and Child responsible for the definition and co-ordination of social and social development policies and practices.

The ISS has as its mission to manage all policies of social development, tackling poverty and social exclusion, as well as to support partnerships. The ISS promotes and manages the development of programs directed towards children and young people, family and community and old age people. It implements programmes to fight poverty and social exclusion and the Social Insertion Income (Minimum Income) as well as other projects related to social development.

The ISS. is also reponsible for the co-ordination and evaluation of the NAPincl process.

Description of on-going projects relevant to the Laps/Raps project partnership

NAPInc - Participation Project on Local Level

The aim of the project was fostering the participation at local level. The strategic steps towards local level were:

a) presentation and discussion of the NAPInc 2003- 2005 in 9 public sessions across the country with local organizations in partnership with the Portuguese EAPN;b) development of 7 local workshops, organised to debate the NAPs, with the main objective to learn from each others experience and to produce and implement integrated social inclusion measures. Around 120 people from local social networks participated;c) Organization of a National Seminar, which was attended by 400 participants from the national and local level.

Social Network Programme

The Social Network Programme is governed by the Council of Ministers (CMR) Resolution no. 197/97 and forms part of Portugal's 'active social policies', based on involvement and acceptance of responsibility by individuals and society as a whole in the fight against social exclusion.

The said CMR defines the social network as "a forum for co-ordination and combination of efforts, based on optional membership by local authorities, public bodies and NGOs which wish to take part". The aim of the programme is to combat poverty and social exclusion through development of partnership structures, in which the local authorities play a central role, and promotion of local social development, through the introduction of joint strategic planning dynamics.

The underlying principles are:

- Integration - implying the convergence of economic and social measures; negotiation between individuals, social groups and society; growth in joint local development projects and combination of resources.

- Co-ordination - refers to complementarity, combined efforts and building partnerships around common objectives.

- Subsidiary - based on proximity to the population and their respective problems and to local answers, as a collective responsibility, at local. regional and national level.

- Innovation - working towards multi-disciplinary, inter-institutional and non-bureaucratic solutions.

- Participation - refers to active involvement, by both local actors and population, in particular by the disadvantaged, in actions to be undertaken in the context of the programme.

The objectives are: (i) implementation of joint planning processes on the basis of reviewable social diagnoses; (ii) Promotion of co-ordinated intervention in municipalities and parishes; (iii) to look for solutions to problems/needs of families and persons in situations of poverty and social exclusion; (iv) promotion of adequate coverage in terms of services and equipment in the respective municipalities; (v) promotion and dissemination of knowledge on the situation in municipalities.

The methodology developed is as follows: each of the municipalities (local levels) should undertake/set up the following: Starter Unit; mobilisation actions with a view to setting up the Local Social Work Council (CLAS); creation of the Local Social Work Council; Procedural Rules; Plan of Work; Preliminary Social Needs Analysis; Social Development Plan; Action Plan; Information System; preparatory work for the Parish Welfare Boards (CSF) or Inter-Parish Welfare Boards (CSIF) and creation of the CSF or CSIF. The CLAS (at municipal level) and the CSF (at parish level) are partnership structures, and serve as platforms for planning and co-ordinating social intervention, in the context of which a model needs to be found for functional co-ordination with other partnerships and Programmes.

Mainstreaming Social Inclusion

The Mainstreaming Social Inclusion Project (1) explores how social inclusion might be brought into a central role in the formation of political and administrative policies in EU Member States. The main objective of this project is to add to the understanding of how social inclusion can be mainstreamed into policies at a number of different levels and how this can be assessed and evaluated.

There are two products from this project - a book and a website. The book reviews the peer process adopted by the Lisbon European Council, including the co-ordination of national social inclusion policies and the national action plans. In doing this, it explores two key factors that are central to mainstreaming social inclusion: the process of developing policy; the involvement of all relevant stakeholders in the formation of public policy. The book also explores how the mainstreaming of social inclusion might be evaluated and proposes a framework for such evaluation, including possible indicators.

(1) The Mainstreaming Social Inclusion Project is part funded by the European Commission through the EU Transnational Exchange Programme (TEP).

The Evaluation of Mainstreaming Social Inclusion In European Union Member States 
This research project (1) will develop an extensive survey of national, regional and local administrations, social partners and civil society organisations, using the evaluation questionnaire, which was developed during the Transnational Exchange Programme project on the Mainstreaming of Social Inclusion. It is proposed that this study will be undertaken by fifteen partner organisations in nine countries, including the present 'MSI five' - Czech Republic; France; Ireland; Norway; and Portugal. Other countries participating are Bulgaria, the Netherlands, Slovak Republic and the UK.  Northern Ireland will participate as a region and the European Anti Poverty Network as an NGO partner organisation.

The results of this study will provide a benchmark for the future measurements of mainstreaming social inclusion into the public policies of the Member States.

(1) The Mainstreaming Social Inclusion Project is part funded by the European Commission through the EU Transnational Exchange Programme (TEP).

Promotion of more active policies for the social inclusion of the Roma and Traveller minorities

The "Promotion of more active policies for the social inclusion of the Roma and Traveller minorities" Project (1) responds to the objective included in the European strategy to combat exclusion of acting on behalf of the most vulnerable groups.

This project promotes the creation of a trans-national partnership comprised of partners responsible for the drafting of the Action Plans of four Member States and partners from four NGOs with experience in the development of actions in the field of exclusion affecting the Roma and Traveller minorities in the same countries. It is envisaged that public and private partners from other Member States and Candidate Countries will join the project.

The main objective of this project is to give impetus to inclusion policies focusing on the Roma and Traveller minorities in the coming NAPincl rounds of negotiation (2003-2005). The foreseen activities for this first stage of the project are:

- Identification of the main fields of social exclusion affecting the Roma and Traveller communities in the four partner countries and the elaboration of a report on their situation.

- Analysis of the measures being carried out within the framework of the NAPincl (2001-2003) and the impact and results obtained for the Roma and Traveller minorities.

- Identification of proposals and guidelines for use in approaching the measures focusing on Roma and Travellers in the next NAPincl (2003-2005) addressed to all E.U. Member States

(1) The Mainstreaming Social Inclusion Project is part funded by the European Commission through the EU Transnational Exchange Programme (TEP).

Main areas of interest of the project partner

The main areas of interest of the Institute are:

- Social protection system;

- Social Services and Infraestrutures Network;

- Social Inclusion;

- Social Network;

- Social development policies and practices in the scope of poverty and social exclusion; children and young people; people with disabilities; elderly; homeless; immigrants and ethnic minorities; family and community;

- Other areas related to social development.

Name of Organisation: 	Public Institution Socio Celje

Representative: 	Suzi KVAS, prof.

Contact details: 	Stanetova 4, 3000 Celje, Slovenia, 
Tel.: 00386 3 492 40 42 
Fax: 00386 3 492 40 43 
E-mail: suzi.kvas@siol.com

Background
Javni Zavod (Public Institution) Socio was founded by Celje municipality in October 2002, as an Institute to provide additional services to Celje's social service users. The institute's work is directed at facilitating the social integration of marginalised groups such as drug addicts, the homeless, single mothers etc.

Activities of Javni Zavod Socio are: providing shelter for homeless people, providing a maternal house, setting up the project office "Celje healthy city", offering a safety point for abused children and providing space for the investigation of abused children. Its main goal is to make an analysis of the current situation and of victim's needs. It provides professional programmes advising victims while they are staying in help centers. It also organises practise exchange with other partner organizations in order to review the forms of supporting programme for non-violent settling of conflicts and to establish self-confidence.

The organisation exists of the following bodies: Council of Institute, Director of Institute and Professional Council. It has ten employees and 3 public workers.

Description of on-going projects relevant to the current project partnership:

SHELTER FOR HOMELESS PEOPLE:

Javni Zavod offers them residence, a warm meal and professional help. The users of shelter and workers are fighting poverty on a daily basis. The organisation is also active in the fight against alcohol abuse, drugs abuse, mental health discrimination, unemployment, etc.

Other Areas of interest:

Our Institute is also working on the European level. We are taking part in several international conferences where we are exchanging work experiences and where we are developing new partnerships.

Name of Organisation:  Comune di Roma ,Department XIV - local development, training and employment policies

Representative: 	 
Federico Bardanzellu

Contact details:  	
Giuseppe Panebianco 
Lungotevere de' Cenci 5 - 00186 - Roma Tel: 0039 (0) 6 67106294, 
0039 (0) 3396520488 
Fax: 0039 (0) 6 68136407 
E-mail: panebianco.urban@tiscali.it

Short presentation of the organisation:

The Political Department in charge for Local Development, Training and Employment Policies, was established by the Municipal Administration deliberation n. 444, on August 9th 2001. On September 15th 2001, the Department received its current name.

The Department manages any kind of activity successfully promoted by the Rome City Council in matter of employment and job counselling, especially concerning integrated projects at a local level.

The employment policies promoted by the XIV Department aim at overcoming the old concept of working "position", with a new concept of "self-employment". In that respect the Municipal Administration implemented integrated actions for the promotion of an active employment strategy. This idea is based on theories assessing that job inclusion and effective quality of employment are among the most important factors, in order to have a local integrated community.

A wider delegated power for Rome as a City is desirable in order to optimize these new actions, in terms of integrated governance of the "metropolitan area". With the new Regional Administration, this objective might be reached, since a new law for Rome is currently being written.

Description of on-going projects relevant to the current project partnership:

THE URBAN PROGRAMME

Ufficio Speciale Urban: the office has managed the entire programme, closed up, within December 31th 2001, with 94 % of the expenditures:

PIC Urban 1994/1999, Sottoprogramma Roma: "The City moves the Towers" in Tor Bella Monaca neighbourhood

In 1998 the Department XIV - Local Development, Training and Employment has consolidated experience in European programmes and it is currently involved in several European projects.

The occasion to test an integrated approach based on participation and valorisation of citizens active role becomes a model which includes the development of the local economy, the ability to attract new operators and investments, the growth of individual competence and know how, the quality of social relationships, the responsibility of different institutional levels.

The URBAN programme was a strong innovation factor, in a context where the policies had focused for years only on urban renewal, providing one of the first occasions to test an integrated approach based on participation. The valorisation of citizens' active role is a key element of the new European strategy. Therefore, the City administration became a catalyst for local development and created new spaces for socialization, increasing the citizens' faith in institutions.

The aim of the project was mainly the creation of new job opportunities for young people, by the support to new firms' creation and self-employment, and the improvement of several facilities by recovering abandoned buildings, ensuring their maintenance and respecting ecological issues.

The support to new firms' creation was our first action for self-employment. Moreover, the existent economic fabric of the area was supported by offering real services to firms, after a previous research on needs.

The issue of employment was addressed by the creation of a Job Centre for the matching between supply and demand, and the organization of 14 training courses, especially preparing young people to use computer, and providing professional counselling.

To improve the situation of the weakest parts of the population, within the Measure 3 "social Services and Security", many new services have been started:

- a day-centre for disabled persons

- a playgroup

- a centre for information, counselling and training on citizens' rights

- a service addressing the problem of academic failure

- a centre for inter-cultural education and animation

- a service for street education

- different programmes for socio-cultural education

Each one of these services was located in recovered buildings. Indeed, 16 renewal projects were carried out, transforming a laundries' building, a railway station, etc.

These renewal projects contributed as well to the creation of cultural centres, sports centres, a large theatre, a centre for elderly persons, a library, and new facilities in the schools, which may be of use for all the inhabitants.

Within the Measure 4 "Infrastructures and Environment", systematic actions for environmental upgrading were implemented to:

- tackle the traffic problems,

- create pedestrian protected routes,

- upgrade a main street of the neighbourhood and lighten it,

- equip the green area of Parco del Celio,

- create new parks and gardens with fountains,

- upgrade a large central square that might become an important social and cultural meeting point,

- purify the water of the Tor Bella Monaca ditch, a natural resource that changed the area into a garden.

In conclusion, 100 000 square meters of green areas were created or upgraded, three squares were planned on about 37 000 square meters, and 2 700 meters of street were upgraded with pedestrian routes, 13 new public spaces were supplied.

The URBAN programme, in Italy, was the first experimental laboratory for integrated policies considering ecological issues, social inclusion, and new citizensâ€™ ethics, and this is what made it successful.

Other Areas of interest:

The Municipal Observatory of Employment and Work Conditions in Rome

This Observatory should be an instrument for better knowledge of the Job Market, in order to defend the workers' rights and a "better employment", tackling the phenomena of moonlighting and promote a culture of legality.

It focuses on research activities about the roman job market, information on the workers' rights, fighting moonlighting, enquiries and control on illegal cases.

High unemployment rates, proliferation of unstable jobs, moonlighting are the problems we wished to address for a better quality of life. This is the reason why we are building a network with public authorities, associations, NGO, unions and cultural solidarity centres with this new Observatory, that foresees:

- researches on the Immigrants' work market, the Features of women's work, and gathering of the existent information

- the creation of 4 Centres for the Workers' Rights, promoting the participation and grouping of precarious workers

- the creation of offices for legalization of workers offering counselling services to SMEs.

- Inspections in firms with the police services, to check possible breaches in law.

- A permanent board with the unions to agree on joint actions.

ROME CITY COUNCIL JOB COUNSELLING CENTRES

The 23 Centres for Job Counselling, distributed over all the urban territory, are intended to be a motor for the local employment development, especially in the suburbs.

Such centres include :

- a person specialized in information management and reception of the users who specifies their demand,

- a Senior counsellor who helps the user defining his training or professional projects

- two Local Development Operators for employment area and business area.

They have a positive impact on their territory and create effective relationships on the employment issue with the Constituencies, Professional Training institutes, employment services, social services, schools, cooperatives and all connected services targeting specifically disadvantaged populations, the third sector and the integrated public programmes themselves. As for business promotion, counselling services are provided to local firms to encourage them hiring on stage and training contracts, and to the users who wish to create their own activity - firm or cooperative - especially with special funding.

The citizen can get in such centre a complete and weekly updated information on job and training opportunities, he is supported in his applications for the CV writing and all the other necessary procedures, and may receive a professional and training advice aimed at supporting individual choices, a counselling for firm creation .

ROME CITY COUNCIL VOCATIONAL TRAINING CENTRES

Rome Town city has been providing for a long time, 20 years, ten professional Training Centre with an agreement signed with Lazio Region.

A long experience in this sector ha allowed, during the years, to improve services demand for users trying to answer to different requirements, thanks to a dedicated activity within the town and the capability to face situations, and in the meantime specialized professional pursuit where started.

The results gained on the training demand and with the capability to create new professional work, have supported the administration to invest resource to amplify opportunity of orientation, training and work introduction.

The management, originally working as private Department Town Council- Province wads signed, and this allows a public management finalized to the social economical development within territory.

Jobs in jail for Rome

This is an aspect on which we are focussing our attention, with a Service for the promotion of work in and out of jail for prisoners, prisoners who benefit from the day-freedom measure, and former prisoners.

In close cooperation with the Prison's Authorities and the Ministry for Justice, we aim at coordinating the different existent measures for work and training of prisoners, map the support existent services and:

- we defined a favourable score for the Bersani firm-creation projects that plan to hire prisoners, prisoners who benefit from the day-freedom measure, and former prisoners,

- we supplied 10 grants for their professional inclusion in cooperatives and associations, and received 40 demands,

- the Centre for Job Counselling that existed only in the Rebibbia jail is now regularly moving to the 4 other jails of Rome,

- we published a complete guide to employment for prisoners that is distributed to the 3 500 roman prisoners,

- we created a joint commission with the Ministry for Justice to sign an agreement for the promotion of work for prisoners,

- we are bringing training courses in jail, and the first one will start on January 2003,

- we are making the Municipal firms aware of this issue, with positive results.

Municipality of Thessaloniki

The municipality has two local action programmes for socially excluded groups. These groups are unemployed women, immigrants, early school leavers, and persons with low skills and qualifications. All of them are attending psychosocial, occupational and legal counselling sessions. A lot of them have already attended or they are going to attend vocational training programmes relevant to their experiences or their interests. After that they will receive funding in order to create their own business or to be hired in local businesses.

´

Name of Organisation: Ministry of Labour and Social Affairs of the Czech Republic

Representative: Ms. Zuzana Zajarosova , Ms. Jitka Zukalova

Contact details:

Na Poricnim pravu 1 
128 01 Prague 2  
Website: http://www.mpsv.cz

Short presentation of the organisation:

Ministry of Labour and Social Affairs (MoLSA) is a central department of the State administration and is responsible for employment and social policy. 

Among others activities MoLSA is responsible for the coordination of the social inclusion strategy in the Czech Republic. It means that it coordinated process of elaboration of the Joint Inclusion Memorandum and the National Action Plan on Social Inclusion and it is also responsible for the implementation and the delivery of the Plan. Since this work requires the participation of all relevant actors at national, regional and local level, the Social Inclusion Committee was established for efficient coordination of this process, which has been coordinating the social inclusion issues.

One of the key elements for efficient social inclusion strategy is high quality cooperation at all levels and involvement of all relevant actors. MoLSA has intention to develop more efficient cooperation between central level represented by MoLSA and regional and local levels in the field of social inclusion. The intention is to encourage the regional and local authorities in developing regional or local Action Plans on Social Inclusion with the use of the instrument of community planning of social services.

MoLSA has also provides funding support for the community planning process. Community planning is directed at the promotion of partnership, development of regional social policies and planning social services at the level of regions and municipalities, NGOs and social services users. It is based on mutual cooperation between responsible institutions (municipalities and regions) users and social services providers. The objective is to develop a continuous planning process and establish full cooperation within all levels.

Description of on-going projects relevant to the current project partnership:

Czech Contribution to European Social Inclusion strategy. The Experience of a New Central European Member State is the national awareness raising action on social inclusion (VP-2004-05) - the aim of this action is to improve information and raise awareness among concerned stakeholders and the wider public about the EU social inclusion process. The project is lead by the Information Centre of Non-profit Organizations - www.neziskovky.cz .

Mainstreaming social inclusion project, phase 2. and Mainstreaming social inclusion research project. The aim of this project was to understand the main principles of mainstreaming social inclusion and how this tool could be used at development of social inclusion policies. The main leading partner of the project is Combat Poverty Agency ( Ireland) www.cpa.ie

Junta de Comunidades de Castilla-La Mancha
Consejeria de Trabajo y Empleo - Direccion General de Trabajo e Inmigración

The "Junta De Comunidades" is the regional government of Castilla-La Mancha, an autonomous region of Spain. The decentralization process began in 1983 directed by the regional government. After more than twenty years, this government has a great regional developing experience with the support of the central government of Spain and the European institutions. It has gained relevant experience in the following fields:

- promoting regional sustainable development with an integrated concept of development

- consolidating the function of institutions so that they have an important framework in the process of the economic and socio-economic development

- promoting cooperation between countries and regions of the European Union

- promoting the establishment of lasting relations between private and public organizations, located in the European Union

- promoting the development of the civil society

- promoting cooperation and dialogue between decentralized public and private organizations, on subjects relative to the regional and local development.

# Footnotes

Income quintile ratio is defined as the ratio of total income received by the 20% of the population with the highest income (top quintile) to that received by the 20% of the population with the lowest income (lowest quintile).

This is calculated using the Gini coefficient, which is a measure of inequality of a distribution, defined as the ratio of area between the Lorenz curve of the distribution and the curve of the uniform distribution, to the area under the uniform distribution. The coefficient is a  number between 0 and 1, where 0 corresponds to perfect equality (e.g. everyone has the same income) and 1 corresponds to perfect inequality (e.g. one person has all the income, and everyone else has zero income). It was developed by the Italian statistician Corrado Gini and published in his 1912 paper "Variabilità e mutabilità".

Benchmarking in Immigrant Integration, Report written for the European Commission by the European Research Centre on Migration and Ethnic Relations (ERCOMER), Han Entzinger and Renske Biezeveld, Rotterdam, August 2003

These case studies were prepared following the second ‘LAPs and RAPs’ workshop, held in Rome in May 2006 that was focused on the integration of vulnerable groups into the labour market.