YEAR TWO ACTION PLAN - REVISED

| September 06 | Venice | (i) Production of second peer review and development exchange report (ii) production of end of year one technical and financial report (iii) Interim evaluation report | Venice with host partner Venice QeC-ERAN |
| --- | --- | --- | --- |
| Sept 06-0ctober 06 | Venice | Planning and Co-ordination of third peer review exchange workshop | Venice with host partner |
| 25 September 06 | Brussels | Third Project Steering group meeting. As well as monitoring progress against agreed action plan this meeting will focus on the local/regional action plans for social inclusion being produced by partners. | Venice with QeC-ERAN and all project partners |
| 15-18 November 06 | Lisbon | Third Peer review exchange workshop | All Partners |
| January 07 | Venice | (i)Production of third peer review exchange report | Venice with host partner |
| March and April 07 | Venice | Planning and Co-ordination of Fourth peer review exchange workshop (ii) production of year two interim reports(activity and financial) | Venice with host partner Venice |
| 18-20 April 07 | Venice | Fourth Peer review exchange and development workshop | All Partners |
| June 14/15 OR 28/29 07 | Brussels | Final Project Steering group meeting. End review of project and also presentation of local/regional action plans for social inclusion Second annual local dissemination and mainstreaming workshops. Presentation of local/regional action plans for social inclusion. | Venice with QeC-ERAN and all project partners All Partners |
| Sept 07 | Venice | (i) Production of Fourth peer review exchange and development report (ii) Production of final technical and financial reports (iii) Production of final project report | Venice with host partner Venice External Expert in conjunction with QeC-ERAN |