A framework for local and regional action plans for social inclusion

Draft for Discussion at the Rome Meeting

Peter Ramsden Freiss Ltd.

April 2006

CONTENTS

1	Introduction	3

2	What is working and what is not working in the NAPS INCLUSION?	3

3	The focus of the local and regional action plans for inclusion	7

4	Participation	8

5	Indicators for combating social exclusion	12

5.1	Problems with the common indicators	14

6	Suggested Steps for developing a Local or Regional Action Plan for Inclusion	16

6.1	Introduction – the planning cycle	16

Step 1 Building the evidence base	16

Step 1:  Building the evidence base	16

Step 2: Stakeholder analysis	17

Step 3 Problem analysis	18

Step 4 Option analysis and strategy formulation	21

Step 5  Intervention logic – going from goals to actions	21

Step 6 Adding indicators, means of verification and setting targets	23

Step 7 Risks and assumptions	26

Step 8 Bringing it all together and achieving coherence by using an adapted logical framework	27

7	Structuring the LAP/RAP Inclusion Report	29

8	Annex 1.  City and sub City indicators from the Urban audit	30

# Introduction

This work has been funded by EU through the Transnational Social Action Programme, which is linked to the EU Social Inclusion Strategy.   It is managed by the City of Venice with scientific and technical support from QeC ERAN.  The full list of project partners is:

- Quartiers en Crise – European Regeneration Areas Network QEC ERAN (BELGIUM)

- Association for the Development of West Athens (GREECE)

- Fondazione G. Brodolini (ITALY)

- Comune di Crotone (ITALY)

- Instituto da Segurança Social (PORTUGAL)

- Javni Zavod Socio (SLOVENIA)

- Comune di Roma – Department XIV – local develpment, training and employment policies (ITALY)

- Municipality of Thessaloniki (GREECE)

- Ministry of Labour and Social Affairs (CZECH REPUBLIC)

- Junta de Comunidades de Castilla-La Mancha –  Consejería de Trabajo y Empleo – Dirección General de Trabajo e Inmigración (SPAIN)

In 2004 Spring Council of the European Union received reports stating that there are over 68 million people living at risk of poverty (i.e. living with an income below 60% of the national median income) in the enlarged EU of 25 Member States.

This report sets out a methodology for developing a Local or Regional Action Plan Inclusion.  There is also a second report which contains case studies of national, regional and local action plans to illustrate how aspects of inclusion have been tackled in other places.

# What is working and what is not working in the NAPS INCLUSION?

The Nice European summit in 2000 fixed four common objectives

- To promote participation in employment and access to all to goods, services resources and rights

- To prevent social exclusion

- To support the most vulnerable

- To mobilise and involve all stakeholders

The approach was intended to be multi-dimensional, universal but also targeted on those most in need, to focus on prevention and alleviation and policy and process.  It was followed up at the Stockholm Council a year later:

"The fight against social exclusion is of utmost importance for the Union. Paid employment for women and men offers the best safeguard against poverty and social exclusion. Those who are unable to work are, however, entitled to effective social protection and should be able to play an active part in society. Active labour market policies promote social inclusion, which combine pursuit of social objectives with the sustainability of public finances. Priority should be given by Member States to implementing National Action Plans on combating poverty and social exclusion in order to progress on the basis of the common objectives agreed in Nice, assessed by commonly agreed indicators.

The European Council invites the Council and the European Parliament to agree in the course of 2001 on the proposal for a social inclusion programme, and asks the Council to improve monitoring of action in this field by agreeing on indicators for combating social exclusion by the end of the year."  Stockholm Council 2001

The development of the European Union’s policy since the Lisbon summit has been based on the Open Method of Coordination.  There are five components that make up the open method, some of which are referred to later in this report:

- Agreeing common objectives for the Union

- Establishing common indicators as a means of comparing best practice and measuring progress

- Translating the EU objectives into national/regional policies on the basis of National Reports on Strategies for Social Protection and Social Inclusion

- Publishing reports analysing and assessing the National Reports

- Establishing a Community Action Programme to promote policy cooperation and transnational exchange of learning and good practice.
(A conference to focus on the lessons drawn from the Community Action Programme to combat Social Exclusion was held in Brussels 29-30 March 2006. The working documents are available on the Events webpage)

Since this start there has been steady progress and considerable activity both at European level and in the Member States:

| Dec 2000 | Common objectives (Nice) |
| --- | --- |
| June 2001 | First NAPs/inclusion developed for EU-15 |
| Mar 2002 | First Joint Report on Social Inclusion |
| July 2003 | Second version of NAPs inclusion developed for EU-15 |
| Dec 2003 | Joint Memoranda on Social Inclusion |
| Mar 2004 | Second Joint Report on Social Inclusion |
| June 2004 | Commission Report on Social Inclusion in EU10 Accession countries |
| Jan 2005 | Report on social inclusion in 10 new MS |
| June 2005 | Implementation and Update Reports on 2003-2005 NAPs (and "light"updates for EU10) |
| Feb 2006 | Commission Report on Implementation Reports and Joint Report on Social Protection and Social Inclusion |
| March 2006 | Adoption of Streamlined Approach including revised objectives by EPSCO and Spring European Council |
| March 2006: | Guidelines for National Reports on Strategies for Social Protection and Social Inclusion |

In the next few years there will continue to be emphasis on poverty and social inclusion.  Revised NAPs for the EU 25 will be produced in late 2006 as part of streamlined national reports covering the period to 2008.  2007 will see the launch of the Progress Community action programme.  And 2010 will be the European year on Poverty and Social Exclusion.

Examples of NAPs inclusions can be found on the web as part of the European Commission’s inclusion website.  A selection of NAPs Inclusion for the members of this partnership are presented below:

- Czech republic

- Greece

- Portugal

- Spain

- Italy

The National Plans vary in their structure to some extent but the main headings are fairly consistent as presented below:

- Main trends and challenges

- Progress in previous plan period

- Strategic approach main objectives

- Policy measures

- Institutional initiatives

- Good practice

- Annexes

Experience of implementation of the first two rounds of National Action Plans

The NAPs Inclusion have succeeded in keeping poverty on the political agenda at a time when competitiveness has tended to dominate the European economic headlines.  They have improved analysis of problems, provided a platform for exchange of learning and show a multi dimensional approach.  Increasing amounts of mainstreaming and coordination are visible in institutional arrangements.   There has been growing consensus about the nature of problems and the ways that they can be solved.   Despite the successes 15% of EU citizens still live below the poverty line.

Proposals have now been made for streamlining the objectives in the Social Protection Committee’s 2006 report .  The report sets out three integrated common objectives for all the areas of work including social inclusion (other areas are pensions, health care and long term care)

- Promote social cohesion and equal opportunities for all through adequate, accessible, financially sustainable, adaptable and efficient social protection systems and social inclusion policies.

- Interact closely with the Lisbon objectives on achieving greater economic growth and more and better jobs and with the EU's Sustainable Development Strategy.

- Strengthen governance, transparency and the involvement of stakeholders in the design, implementation and monitoring of policy

For social inclusion the key idea is to make a decisive impact on the eradication of poverty and social exclusion.  Within this a number of specific objectives are identified:

- Ensure the active social inclusion of all by promoting participation in the labour market and by fighting poverty and exclusion among the most marginalised people and groups.

- Guarantee access for all to the basic resources, rights and social services needed for participation in society, while addressing extreme forms of exclusion and fighting all forms of discrimination leading to exclusion.

- Ensure that social inclusion policies are well-coordinated and involve all levels of government and relevant actors, including people experiencing poverty, that they are efficient and effective and mainstreamed into all relevant public policies, including economic, budgetary, education and training policies and structural fund (notably ESF) programmes and that they are gender mainstreamed.

#### Why do we need a local or regional level?

(NAPs) Inclusion has demonstrated that strong vertical and horizontal integration of economic, employment, lifelong learning, cultural, housing, health and social policies is needed to make progress in eradicating social exclusion and poverty.

The NAPs inclusion are not widely known about or understood either by policy actors involved in inclusion, the social partners or by the target groups themselves.  The local level offers an opportunity to engage actors and beneficiaries in a serious discourse about practical action that is impossible in the rarefied atmosphere of government departments at national level.

At local and regional level there is a recognition that policy delivery is shared between a wide range of agencies and that only through better coordination and mainstreaming can improvements be made.

The overwhelming tendency for most programme-based approaches that focus on social exclusion has been to create a new set of initiatives supported through short term project funding.  These can be seen in both domestic and EU programmes including initiatives such as Urban and Equal.  Project based approaches can bring temporary relief but rarely change the underlying factors that lead to exclusion, or the behaviours of delivery bodies that perpetuate it.

Local authorities and municipalities deliver many of the services on which the poor and socially excluded rely and are therefore well placed to coordinate and develop local action plans for social inclusion although in for some of the objectives – for example employment and enterprise it is likely that other bodies are better placed to be take the lead role.  This will also vary according to the Structure of Member State governance and competences.

The review of Lisbon at the Brussels European Council in 2005 reaffirmed the importance of the social dimension, social cohesion and social inclusion

"Social inclusion policies should be pursued by the Union and by Member States, with its multifaceted approach, focusing on target groups such as children in poverty"

# The focus of the local and regional action plans for inclusion

The focus is drawn from five of the six priorities identified in the European Union’s Action Programme Against Social Exclusion.  The missing priority is more concerned with actions that can be organised at national level and had therefore been excluded.  The five remaining priorities are:

- Employment:  Promoting investment in and tailoring of active labour market measures to meet the needs of those who have the greatest difficulties in accessing employment

- Access to services:  Increasing the access of the most vulnerable and those most at risk of social exclusion to decent housing, quality health and lifelong learning opportunities

- Education to work transition; implementing a concerted effort to prevent early school leaving and to promote smooth transition from school to work

- Children: Developing a focus on eliminating social exclusion among children

- Immigrants and ethnic minorities: Making a drive to reduce poverty and social exclusion of immigrants and ethnic minorities

Our suggestion is that one of these five priorities should constitute the backbone of the local and regional action plans.  Choose the one that is most pressing in your area.

It is likely partners will decide on that further specialisation.  For example a region may choose to focus on access to services by a specific group such as immigrants, Roma or the homeless rather than for all people.

# Participation

Sherry Arnstein, in a seminal paper written in 1969, identified eight levels of engagement with citizens.  She characterised these in a ladder from non-participation through tokenism to citizen power.

Figure 1: Arnstein’s Ladder of Participation

1 Manipulation and 2 Therapy. Both are non participative. The aim is to cure or educate the participants. The proposed plan is best and the job of participation is to achieve public support by public relations.

3 Informing. A most important first step to legitimate participation. But too frequently the emphasis is on a one-way flow of information. No channel for feedback.

4 Consultation. Again a legitimate step - attitude surveys, neighbourhood meetings and public enquiries. But Arnstein still feels this is just a window dressing ritual.

5 Placation. For example, co-option of handpicked 'worthies' onto committees. It allows citizens to advise or plan ad infinitum but retains for power holders the right to judge the legitimacy or feasibility of the advice.

6 Partnership. Power is in fact redistributed through negotiation between citizens and power holders. Planning and decision-making responsibilities are shared e.g. through joint committees.

7 Delegated power. Citizens holding a clear majority of seats on committees with delegated powers to make decisions. Public now has the power to assure accountability of the programme to them.

8 Citizen Control. Have-nots handle the entire job of planning, policy making and managing a programme e.g. neighbourhood corporation with no intermediaries between it and the source of funds.

Source Participation guide: 10 key ideas

A less controversial formulation restructures the eight into the five levels below:

- Information

- Consultation

- Deciding together

- Acting together

- Supporting independent community interests

In action planning it is likely that ‘deciding together’ will be used for the formulation of the action plan.  The delivery will almost certainly require level ‘acting together’ or even ‘supporting independent community interests’ such as community based NGOs.   This ladder underlines the importance of establishing and maintaining trust with the other agencies and crucially with the beneficiaries

#### Structuring stakeholder meetings looking at problems and needs

A number of well established consultation techniques have been developed for use in public participation and consultation settings.  Some of the best like ‘Planning for Real’ involves practical exercises that make situations seem more real.  The classic application of Planning for Real is in neighbourhood revitalisation programmes.  A large-scale map of the area is used to create a three dimensional model.  This can be quite rough and ready and if necessary just a base map can be used perhaps with different land uses marked in different colours.  If the group is fairly small they can be involved in building the model.

The participation exercise is then run as a discussion between stakeholders over the model.  Sometimes it will be filmed so that a record of the ‘meeting’ can be kept.   The use of a model allows different scenarios to be played out: for example the selective demolition of a street, or the creation of a pocket park.   The use of a practical tool such as the large-scale model enables a free flow of discussion and ideas between people that have very different levels of power and experience.    Planning for real allows professionals and residents to discuss complex issues in a way that is rarely possible in more formal and traditional settings.   Although Planning for Real was designed for use in physical planning, it is frequently adapted to other contexts – for example it is an excellent way of getting people to look at community safety issues.

#### Use visualisation techniques such as Meta planning

Another classic facilitation approach is called ‘meta planning’ and involves the structured use of cards or large post-it notes to help to visualise the problem.  These are essentially simple brainstorm techniques but they are very effective at ensuring that a wide range of views is obtained from the group.  These approaches have been further developed within various of the ‘Project Planning’ (e.g. GOPP and ZOPP) approaches that use large cards completed by participants that are then spray glued to a matrix huge backing sheet mounted on the wall.  These methods when deployed by a skilled facilitator can produce more participative meetings than the more traditional audience and presenter layout.   They also serve as a summary of the meeting.  More complex ideas can be developed and captured and more members of the group will participate actively.   We will return to GOPP and ZOPP in the discussion of the Objectives below.

#### Employ professional facilitation

It is very difficult for one of the leading partners to take the role of facilitator because inevitably they have an interest to protect or promote.  It is best to recruit an independent facilitator who will be more skilled at conducting meetings and will also not have an axe to grind.   More preparation work will be needed to ensure that the facilitator thoroughly understands the policy area that is being reviewed.   If an internal facilitator is used it is important that this person does not use the position to advance a sectional or departmental interest.

#### Consider a number of smaller meetings held at different times

Smaller focused meetings are often more useful.  Holding them at different times allows a range of different interest groups to be involved – for example women.   Large-scale public meetings can become confrontational and do not necessarily produce good information from a range of more hidden groups and voices.

#### Allow sufficient time for the meeting

Most public consultation meetings are short - often lasting only one or two hours because it is felt that people can only give a small amount of time and that larger periods are hard to manage.  Public officials are often afraid that the meeting will degenerate into a slanging match and so want to keep the encounter as brief as possible.   Highly structured consultation meetings can be much longer – often lasting two days or more.  This may seem extravagant but when contrasted with the cost of policy failure the input is reasonable.  Long meetings like this have to be very well planned and highly structured otherwise boredom and frustrations will become a serious problem.   They require professional facilitation

#### Consider a meeting venue out of town

More intensive work can often be achieved by moving the venue to a neutral and more pleasant location.   This prevents the day-to-day intrusions of the home city and workplaces from intervening.  Fresh country air can also help people to think more clearly.  If an out of town venue is not possible then a neutral venue and commitment from participants to stay for the whole session and fully participate is important (no side meetings, no mobile phone interruptions, no emailing in the breaks).

#### 360 degree meetings

Within the framework of a sister project Udiex Alep some developmental work has been carried out on 360-degree stakeholder meetings.  These have been written up and will shortly be available [add hyperlink when site goes live].  The diagram over the page illustrates how stakeholders can fit into this model.  Many of the other techniques discussed above can be combined with the 360-degree approach.

Figure 2: 360-degree stakeholder Structure for the LAP Inclusion

# Indicators for combating social exclusion

“Everything that can be counted does not necessarily count, everything that counts cannot necessarily be counted” Albert Einstein

Indicators enable decision makers to measure progress towards the achievement of outputs, objectives and goals.  Without them we are unable to say whether a policy or action plan is working or not.

However, indicators only indicate, they are always in some ways a proxy measure of the real thing we want to understand.  For example measures of income and wealth are frequently used to measure socio economic progress – the most classic measures being Gross Domestic Product (GDP) and its sister Gross national product.  But neither of these indicators comes close to describing how happy people or societies are.  Both GDP and GNP are inflated by large pollution incidents or by commuting both of which to the citizen are negative experiences.

So indicators are a necessary evil but they need to be handled carefully and we should always apply a quality of life reality check to see whether the indicator really describes a situation.   A useful starting point for quality of life indicators was developed as part of the Urban Audit carried out by participating cities, contractors and academics and supported by the European Union.  The Urban Audit has a direct link to the Lisbon agenda and provides useful source material for additional indicators of social exclusion.  One good example is an indicator measuring the number of pensioners living alone.    A summary table is presented in Annex 1.  City and sub City indicators from the Urban audit.

National administrations also maintain large data sets that focus on exclusion.  One excellent example is the UK’s Index Of Multiple Deprivation, which collapses 37 variables into six domains and is available for small spatial areas of about 1500 people.   The six domains used in the index are:

- Income
captures the proportions of the population experiencing income deprivation in an area.

- Employment
 measures employment deprivation by considering people of working age who are involuntarily excluded from the world of work, either through unemployment. ill health or family circumstances.

- Health and disability
 identifies areas with relatively high rates of people who die prematurely or whose quality of life is impaired by poor health or who are disabled, across the whole population.

- Education, skills and training
captures the extent of deprivation in education, skills and training in a local area. The indicators fall into two sub-domains: one relating to lack of attainment among children and young people and one relating to lack of qualifications in terms of skills in the resident working age population.

- Barriers to Housing and Services
measures barriers to housing and key local services. The indicators fall into two sub-domains: ‘geographical barriers’ and ‘wider barriers’ which includes issues relating to access to housing such as affordability.

- Living environment
focuses on deprivation in the living environment. It comprises two sub-domains: the ‘indoors’ living environment which measures the quality of housing and the ‘outdoors’ living environment which contains two measures about air quality and road traffic accidents.

- Crime
This Domain measures the rate of recorded crime for four major crime themes – burglary, theft, criminal damage and violence - representing the occurrence of personal and material victimisation at a small area level.

Indicators can be either direct or indirect.  Direct indicators are used to look at directly observable changes.  They can usually only be measured at output and activity level.  Indirect or proxy indicators are used for measuring when it is not possible to directly measure, where the time scale of direct indicators is too slow or it costs too much to collect.

For the purposes of the European Action plan on social exclusion The Social Protection Committee has adopted a set of 10 primary indicators and 8 secondary indicators in a Report On Indicators Of Poverty And Social Exclusion  (2001).

- Low income rate after transfers with low-income threshold set at 60% of median income (with breakdowns by gender, age, most frequent activity status, household type and tenure status);

- Distribution of income (ratio of highest 20% to lowest 20% of incomes)

- Persistence of low income

- Median low income gap

- Regional cohesion

- Long term unemployment rate

- People living in jobless households

- Early school leavers not in further education or training

- Life expectancy at birth

- Self perceived health status

Secondary Indicators

- Dispersion around the 60% median low income threshold

- Low income rate anchored at a point in time

- Low income rate before (tax and social security) transfers

- Distribution of income

- Persistence of low income (based on 50% of median income)

- Long term unemployment share

- Very long term unemployment rate.

- Persons with low educational attainment

## Problems with the common indicators

There are a number of acknowledged problems with the common indicators:

- Missing variables:  In the report on common indicators the Social Protection committee recognised that there were some weaknesses in their approach which largely arose because standard data sets for other data are not available across all Member States.  In relation to housing they suggested that NAPs should provide quantitative data on decent housing, housing costs and homelessness as well as other precarious housing conditions.

- They also proposed to do further work on a range of other matters relevant to social exclusion such as access to services, debt, gender issues, literacy and numeracy and access to education and issues around people that live in various forms of institutions (prisons, elderly and supported housing, and children’s homes).

- Spatial and group data:  For LAPs and RAPs there is an additional problem, which is that some of the indicators are not available for regions and localities.  Very few are available at the neighbourhood level which may be a useful spatial level for some of the LAPs and RAPs Inclusion.  In addition some of the key aspects of social exclusion are about issues within the population affecting certain groups.  Again the data may not be available in this disaggregated form.

#### Tertiary indicators

Partly because of these difficulties the Social Protection Committee proposed a third level of indicators that could be agreed by the Member States using available data sources in each country.  This offers the potential for local action plan partnerships to adopt a more operational set of output and impact measures.  There may be a need to include other measures that are relevant to modern living such as Internet and phone access, and a stronger focus on finance and indebtedness reflecting growing concerns about financial exclusion.

The key point on indicators is that they should be chosen to measure progress in relation to the policy goal or objective that has been fixed.  In this sense the most valid indicators are not necessarily the 18 agreed indicators but those that are developed and measured locally and directly relate to the objectives that have been fixed.  The advantage of using local indicators is also that they may have little or no time lag because they can often be built on datasets that are already on line.  This is a particular advantage compared to national datasets, which often have substantial time lags in publication because of the scale on which they operate.  Census data is often released up to two years after the survey and may only be carried out once in each decade.

Table 2 below relates these primary and secondary indicators to the five themes of the EU Strategy to combat poverty and social exclusion

Table 2 Primary, secondary and tertiary indicators for measuring Inclusion related to each of the five themes

|  | Primary indicators (from list) | Secondary indicators (from list) | Examples of relevant Tertiary (locally developed indicators) |
| --- | --- | --- | --- |
| Employment – active labour market measures for those with greatest difficulty | Long term unemployment rate People living in jobless households | Long term unemployment share Very long term unemployment rate | Success rate of LTU in gaining secure employment at minimum wage or higher |
| Access to services: increasing access of most vulnerable to housing, health and lifelong learning | Life expectancy at birth Self perceived health status |  | Proportion of specific population (e.g. homeless) registered for primary health care compared to average in wider community. Proportion of health providers that do not discriminate against the specific community (e.g. homeless, refugees) Proportion of those declared homeless that are resettled in permanent housing. Take up of adult literacy and other learning programmes by homeless people. |
| Education to work transition – preventing early leaving and encouraging smooth school to work transition | Early school leavers not in further education or training | Persons with low educational attainment | Numbers dropping out of full time education at or before 16 Proportion of drop outs that are not working Proportion of school leavers going into full time employment |
| Children – eliminating social exclusion among children | Persistence of low income People living in jobless h/h | Distribution of income (Gini coefficient) Low income rate anchored at a point in time | Children in jobless h/h Children in h/h below 60% of median income Reduction in children eligible for local benefits (e.g. take up of free school meals in UK, households in receipt of housing benefit) |
| Immigrants and ethnic minorities – poverty reduction | Median low income gap (of immigrant community compared to national average | Gini coefficient to measure income disparities with host community | Measures of community prosperity (e.g. home ownership, business ownership, car ownership etc. |

# Suggested Steps for developing a Local or Regional Action Plan for Inclusion

## Introduction – the planning cycle

Experience of a range of strategies and action plans suggests that a number of steps need to be taken in a systematic way for Local Action Plans to be successful.  What is set out below is a comprehensive approach to developing a Local or Regional Action Plan for Inclusion.  Because of pressures in the real world it is rarely possible to pursue all stages in the detail that is needed.  Time is frequently the main enemy, because of a real or perceived need to get into the implementation stage and stop being just a talking shop.

The Planning Cycle brings together all aspects of planning into a coherent, unified process.  By planning within this structure, you will help to ensure that your plans are fully considered, well focused, resilient, practical and cost-effective. You will also ensure that you learn from any mistakes you make, and feed this back into future planning and Decision Making.

Once you have devised a plan you should evaluate whether it is likely to succeed. This evaluation may be cost or number based, or may use other analytical tools. This analysis may show that your plan may cause unwanted consequences, may cost too much, or may simply not work.  In this case you should cycle back to an earlier stage. Finally, you should feed back what you have learned with one plan into the next through a review or evaluation process

The Steps are listed below and described in more detail in the sections that follow:

### Step 1 Building the evidence base

Step 2 Stakeholder analysis

Step 3 Problem analysis

Step 4 Option analysis and strategy formulation

Step 5 Intervention logic – going from goals to actions

Step 6 Adding indicators, setting targets and working out means of verification

Step 7 Risks and assumptions

Step 8 Bringing it all together and achieving coherence by using an adapted logical framework

### Step 1:  Building the evidence base

Purpose of the step: to find evidence to find out what is happening to target groups affected by the problems

Main technique: desk research

This phase involves desk research to find out as much as possible about the nature of the problems facing the target groups that you are thinking of tackling.

#### Policy mapping

Identify what agencies are already doing to address the problems and map it out to look at coverage.  Policy mapping needs to identify all the actions by possible stakeholders that affect the situation of target groups.  These actions may be quite tangential.  For example in a strategy to increase school staying on rates it may be important to look at private and public sector recruitment practices.  Young people may be leaving because they think that qualifications will make no difference in a labour market where discrimination is not curbed.

#### Identify what is working and what is not working

Much delivery focuses on doing the things that have always been done.  The discussion with partners works much better if there is some externally generated evidence (for example evaluations) that inform discussion and provide an evidence base so that criticism is not seen as one person’s opinion but is firmly rooted. It is also helpful to map the level of coverage of existing actions.  Often there are good practices but they only operate for some communities or as pilot projects.  If possible the cost of different approaches should be identified.

Summary of key questions to help build the evidence base:

What does the quantitative evidence base suggest have been the trends of the relevant target groups in relation to social exclusion in your local area or region over the past few years and beyond?

What appears to be the nature of the deprivation in your local area?

How does your chosen goal represent an opportunity for tackling this disadvantage?

What are the barriers (or market failures) underlying these trends that are holding back the target groups in your local area or region?

What previous policy efforts have been tried and tested?  Which did and did not work and why?

### Step 2: Stakeholder analysis

Purpose of the step: to identify who the stakeholders are and what are there interests

Techniques: desk research and analysis

Stakeholders can be defined as all those that have an interest (or stake) in an activity, project or programme – in our case the action plan.    This includes intended beneficiaries, and intermediaries, winners and losers and those involved or excluded in the decision making process (DFID 2004).

Stakeholders are frequently divided into primary stakeholders who are affected by the policy – either positively or negatively and secondary stakeholders – those that have an intermediary role including delivery agencies, policy makers, and field workers.  Some versions limit the number by defining some of each group as Key stakeholders otherwise the potential numbers can be limitless.

Another way of categorising stakeholders is to use the 360-degree approach discussed above in the Participation section.  The beneficiaries or primary stakeholders are shown to the South of the centre.  All the secondary stakeholders are shown to North, West and East.  The Northern stakeholders are policy makers and funders, while East and West are horizontal partners – normally other departments, agencies, NGOs and projects.

Stakeholders have different interests so it is useful to define what their involvement is with the project and how their interests differ.  By systematically analysing the stakeholders it is also possible to see whether there are any missing voices.  The exclusion of the client group is perhaps the most frequent missed voice.  It is also important to assess the capacity of different stakeholders to engage in the process.   A common failure of consultation exercises is to assume that one size fits all and fail to adapt approaches to particular groups.  For example the private sector finds very long agendas and meetings frustrating and attendance drops away.  Women are often not consulted even when the subject is highly relevant to them   Sometimes special meetings are necessary to capture the voice of a particular group.  Table 3 below sets out a format for analysing different stakeholder interests

Table 3 Stakeholder interests for a hypothetical local employment project

| Stakeholders | Interests and how affected by the problem | Capacity and motivation to bring about change | Possible actions to address stakeholder interests |
| --- | --- | --- | --- |
| Primary stakeholders |
| Potential employers | Believe that grants may be available | Important to understand barriers and solutions | Meetings with employers to discuss incentive mechanisms |
| Local unemployed and inactive people | The direct beneficiaries who should access work as a result | Important to test whether new approaches work and to secure “buy in” of users | Focus group meetings and research to deepen understanding of barriers |
| Secondary stakeholders |
| Employment agencies | Threatened by criticism, looking for funding | Resistant to change | Implementation of new outreach policies |
| NGOs interested in employment creation projects | Possible implementing bodies, looking for funding | Important for future delivery of plan and policy innovations | Commission pilot projects |
| Local government | Possible implementing body | Statutory responsibility for economic and social benefit. Local knowledge but limited involvement in employment | Engage as commissioning body |
| Government ministries | Funder and policy maker | Interested in ‘what works’ but little local knowledge | Create long term funding mechanism |

### Step 3 Problem analysis

Purpose:  to identify all the problems and the way that they are linked to causes and effects

Techniques: Summarise evidence from step 1 followed by stakeholder meetings and analysis

The LAP should include a clear outline of the nature and scale of the problem in the LAP area.   A fresh and comprehensive understanding of the existing situation and the problems that exist is essential to enabling the right solutions to be found.

Stakeholder involvement in this stage will expand the way that the problem is perceived and ensure that problems are not merely ‘agency’ views.  It is particularly important to involve the users or beneficiaries (the primary stakeholders) in problem and needs analysis.

The action plan needs to recognise that problems facing the groups are complex, intractable and inter-connected.  No simple solutions are likely to work and ‘business as usual’ approaches by existing agencies need to be challenged because it is the nature of the problems facing the groups combined with the inadequacy of social policy responses that have created the problems found today.

There are many different ways of viewing the same problem.  Depending on the perspective different solutions will be deployed.  For example in the UK over the past 30 years the consensus on the causes of poverty moved away from being the result of a ‘culture of poverty’, to being seen as being caused by economic forces acting on communities in the transition from an industrial to a service economy.  Different interpretations of the problem lead to different solutions.  Under the social pathology model policy focused on the normalisation of deviance.  With the economic model intervention has focused on helping individuals to access jobs and on making work pay.   The choice between different options is assisted by research evidence.

One well established technique for working with problems in a group setting is to make a  problem tree.  This is a simple graphical representation of the problems, their causes and effects.

Stages in drawing up a problem tree

- List all the problems that come to mind. Problems need to be carefully identified: they should be existing problems, not possible, imagined or future ones. The problem is an existing negative situation, it is not the absence of a solution

- Identify a core problem (this may involve considerable trial and error before settling on one).

- Determine which problems are “Causes” and which are “Effects.”
Arrange in hierarchy both Causes and Effects, i.e., how do the causes relate to each other - which leads to the other, etc.

Figure 3 Example problem tree on School drop out

| Academic curriculum switches off kids |  |  | Truanting |  | CAUSES |
| --- | --- | --- | --- | --- | --- |
|  |  | HIGH DROP OUT RATES |  |  | CORE PROBLEM |
| Low literacy and numeracy levels |  |  | Youth unemployment |  | EFFECTS |

#### Bring evidence to the table

Understanding the problem needs evidence to inform the discussion.  This evidence can be from statistics and studies that you have commissioned and collected at the start of the work in step 1.   There may be a need to commission fresh research, although the long lead times for research may make this unfeasible.  Normally it is best to commission an outside consultant or one of the partners to do a quick review of available and relevant published studies and ‘grey’ literature – reports that have not been published.

It is also useful to analyse data on the problem and to look at existing data in new ways – for example by breaking it down into small spatial units to see where the problems are concentrated geographically.  Data should also be presented to illustrate the relationships with demographic characteristics, economic circumstances and other issues that affect the target groups.

Table 4 Problem and solution table for High School drop outs

| Problems | Possible Solutions | Where is best or good practice? |
| --- | --- | --- |
| Too many young people dropping out of school at 16 because inflexible curriculum | Make curriculum more interesting | Finland – most successful education system with low drop out and high average achievement |
| Lack of teachers able to teach new curriculum | Train existing teachers and recruit new ones. | Not known |
| Many students truanting in final years and not reachable by school | Develop outreach programme and offsite provision | Not known |
| Drug and alcohol abuse is affecting students | Work on drug prevention programmes | Netherlands |
| Teenage pregnancies are making girls drop out | Better sex education, outreach provision so that girls can stay in touch during pregnancy and after | Netherlands |
| Teenage counter culture and ‘cool’ street culture do not encourage students to work hard at school | Work with role models to challenge slacker culture | Nowhere yet |

### Step 4 Option analysis and strategy formulation

Purpose:  to identify the different strategy options that may be available and then to make choices between them in order to fix on a strategy.

Techniques:  Stakeholder meetings and analysis

##### Be explicit about the options available

Strategy development involves making choices between a range of options.   Even if the only counter example is the ‘do nothing’ option or retain the status quo.  It helps in drawing up the action plan to be explicit about policy options and to look for evidence based ways to select between them.   However, it should be noted that the evidence-based approach is often better at rejecting options than selecting them.

A range of solutions can solve any problem.  For example reducing unemployment can be addressed by increasing the ‘employability’ of the unemployed, and/or by creating jobs for people to go into.  Often a combination of different supply side and demand side measures are needed to create long-term change.

Strategy is about deciding the particular policy mix and balance of resources that best addresses the problems in a particular area.  Sometimes less is more – concentrating resources on a few effective actions is better than spreading the jam too thinly by supporting too many under funded initiatives.  Many partnership based strategies fall into the trap of doing too much and supporting too many actions by trying to satisfy all the stakeholders.  This is a particular risk in partnerships where

The strongest partners are horizontal stakeholders that supply of services to the target groups and have a vested interest to use the action plan to lever resources.

##### Examine research to find out what has worked elsewhere

Because exclusion is so intractable fresh ideas are needed to tackle it.  There is some truth in the adage ‘there is nothing new under the sun’ Most solutions have been tried somewhere – sometimes in other parts of Europe sometimes in the USA or the developing world.  These approaches should be examined and where appropriate adapted for use in your locality or region

.

### Step 5 Intervention logic – going from goals to actions

Purpose: to work on the goals, objectives, outputs and activities of the action plan and to ensure that the intervention logic connecting them is explicit and clear.

Techniques: This step is best done with the stakeholders in a facilitated meeting

The step is set out in four sections

From Goals to Objectives

From Objectives to Outputs

From Outputs to Activities

Activities

The broad goal of the action plan is probably already fixed and will be based on one of the five themes from the European level.    These are listed below with suggestions of how explicit goals can be derived from them

Table 5 Moving from themes to goals

|  | European action plan broad themes | Explicit goals |
| --- | --- | --- |
| 1 | Promoting investment in and tailoring of active labour market measures to meet the needs of those who have the greatest difficulties in accessing employment | All unemployed and inactive people have good access to employment opportunities and are supported by active labour market measures. |
| 2 | Increasing the access of the most vulnerable and those most at risk of social exclusion to decent housing, quality health and lifelong learning opportunities | All members of xxx group have full access to health services |
| 3 | Implementing a concerted effort to prevent early school leaving and to promote smooth transition from school to work | Every student has a good transition from school to work |
| 4 | Developing a focus on eliminating social exclusion among children | No child grows up in a socially excluded household |
| 5 | Immigrants and ethnic minorities: Making a drive to reduce poverty and social exclusion of immigrants and ethnic minorities | Immigrants and ethnic minorities do not suffer from poverty and social exclusion |

#### From Goals to Objectives

The next stage is to define an objective that the action plan will focus on.  The Objective should be achievable over a known time period.  One way of thinking about the Objective is to vision the changed situation that you would wish to see at a future time.   We suggest that the plan should focus on a 5-year time horizon but you can make it longer.   The Objective may also be more specific, for example by only focusing on one target group or on one service.

Table 6: Examples of possible objectives derived from the goals and themes

|  | Theme /Goal | Examples of possible objectives |
| --- | --- | --- |
| 1 | Employment | X% of current numbers of long term unemployed and inactive people are in permanent work by 2011 |
| 2 | Access to services | Full access to primary care medical services for Y% of the Roma community by 2011 |
| 3 | Education to work transition | School drop out rates are reduced to Z% of current levels |
| 4 | Social exclusion and children | Child poverty among children of single parents is reduced by W% |
| 5 | Immigrants and ethnic minorities | Somali refugees have the same unemployment levels as the host community |

#### From Objectives to Outputs

Here we focus on what outputs need to be delivered by the action plan partnership in order to deliver the objective.   In our child poverty example the outputs could be achieved by raising of parental incomes as a result of helping single parents into work and ensuring that the tax and benefit system supports this move.  Some changes might be outside the control of the action plan partnership – for example tax changes by central government. These will be built into the plan later as assumptions and risks.

#### From Outputs to activities

The final stage moves us from outputs (what we want to achieve) to activities (how we will achieve the outputs).   This is the crucial place where incoherence can creep into plans as partners try to ensure that their projects are included as activities regardless of whether they contribute to critical outputs.   Activities that do not contribute to outputs can be excluded or revised now or later when the indicators are drawn up.

Defining activities is both top down and bottom up

The key is to ask what activity is required to deliver each output

Working out the actions to be pursued is not entirely a top down activity.  Partners have ideas about the activities that they wish to pursue in order to meet the action plan objective. What is needed is an iterative and at times negotiated process to bring appropriate activities into the action plan while excluding those that do not make significant contributions to the objective.  An action plan layout is set out below in table 7:

.

Table 7 Activities table

| Lead partner | Description of activity | Intended outputs | Target Number of beneficiaries | Timescale start and end | Resources |
| --- | --- | --- | --- | --- | --- |
| Benefits office | Improving welfare to work pathways for single parents | Changes to local benefit rules to ensure that work is incentivised | 2000 | Start at end of Year 1 ongoing | €400000 |
| Training organization/ colleges | Training and coaching for young parents in basic and vocational skills | Number of training places | 400 per year | Year 2-5 | €200000 |
| Community based NGO | Job link organization to place residents in jobs | One stop shop for training, advice and guidance and job placement | 600 per year | Up and running by end of year 1 Ongoing | €500000 Secondee from govt training agency |
| Business one stop shop | Encouraging self employment among young parents | Training programme, awareness raising, business support | 150 per year | Up and running by third quarter ongoing | €200000 |

### Step 6 Adding indicators, means of verification and setting targets

Purpose: to add indicators, means of verification and set realistic targets to be achieved

Techniques:  The development of indicators is a technical task carried out by analysts in close consultation with stakeholders

The next step is to attach indicators to the objective, outputs and activities.  As well as identifying the indicators the sources of data to verify that the target has been reached are also identified in the third column: means of verification

These can either be from the 18 Common indicators developed at European level and discussed above or from the tertiary indicators that you can obtain at local level and should develop in the context of the intervention logic table.

In general we would suggest using local data where available as this may have shorter time lags to publication than national data as well as being more suited to the local objectives.  Where possible it is best to adapt existing data collection systems that agencies use rather than doing one off surveys which are expensive to implement and can often be done only once.

Our suggestion is that for the Action plan objective and the outputs you identify indicators and means of verification.  This means that you do not need to work on indicators at the level of goals or activities.

For each indicator you should identify sources of information that enable you to verify that the Objective has been achieved or that the outputs have been delivered.   The table below summarises what the indicators are trying to do.

Table 8 Summary of how to relate indicators to intervention logic

| Intervention logic | Indicators | Means of verification |
| --- | --- | --- |
| Overall goal: Superior strategic goal for the action plan (based on one of the five themes) |  |  |
| Action Plan Objective: The changed situation which the action plan is trying to bring about | How to recognise that the action plan objective has been achieved by qualitative and quantitative judgements | Sources of information to show progress towards objective |
| Outputs: Products services and other deliverables generated by the action plan partnership to deliver the objective | What kind and quality of outputs and by when will they be produced? | Sources of information and methods used to show delivery of outputs |

Table 9 below illustrates how the indicators can be build into the table using a worked example of reducing social exclusion among refugees and ethnic minorities

Table 9 Worked example of indicators for measuring reduction of social exclusion among refugees

| Intervention logic | Indicators | Means of verification |
| --- | --- | --- |
| Overall goal: Reducing social exclusion among refugees and ethnic minorities |  |  |
| Action Plan Objective: To raise the income levels of refugees by increasing their employability and helping them start enterprises | How to recognise that the action plan objective has been achieved by qualitative and quantitative judgements Refugees have higher levels of income because of higher employment and self employment | Sources of information to show progress towards objective Ideally survey data on the refugee community – but this might be too expensive - some proxy might be needed |
| Outputs: improved language skills, vocational skills, job placements, | What kind and quality of outputs and by when will they be produced? Language and vocational qualifications by refugees, Quality courses delivered, numbers placed into jobs. | Sources of information and methods used to show delivery of outputs Number of courses completed by refugees, one to one business advice sessions, Analysis of Monitoring data of employment agency and business start up agency showing job placements and enterprise starts |
| Activities language classes, training programmes, enterprise advice, incubation centre focused on refugee community | This space is used for resources, inputs and timescales (see activities table) |  |

#### Target setting

Once the indicators and means of verification have been defined and agreed the next stage is to fix the targets.  Targets are the explicit quantitative or qualitative achievements to be achieved by the action plan.  They should be achievable but challenging at the same time.   There is a danger with targets, which is that they can induce ‘perverse’ behaviour.  For example in the UK in order to achieve a government target for family doctors of seeing 80% of patients within 2 days of seeking an appointment some doctors surgeries refused to allow patients to book appointments more than 2 days in advance.  This was inconvenient for patients that had to work and organise appointments around a busy schedule.

In some policy areas targets can be very political.  Setting an over ambitious target and then failing to achieve it can have serious effects.

#### Summary on indicators and methods of verification

Indicators are essential but painful.  The advantage of the indicator matrix is that it forces you to link your indicators to your intervention logic.  At the same time it allows considerable freedom to select indicators that are relevant to what you want to measure rather than those available from the 18 common indicators of the European level.

- Use as few indicators as possible – they are expensive to collect and process.

- Use a variety of indicator types and remember to measure quantitative and qualitative change – qualitative change can be more useful

- Find indicators that relate directly to the outputs and objectives, this will often mean creating local indicators rather than using the 18 from the EU common framework.

### Step 7 Risks and assumptions

Purpose: to identify the risks that may affect the action plan and the assumptions on which the plan depends

Techniques: Analysis checked in consultation with the key stakeholders

Action plans partners can only control their own behaviour.  Inevitably the action plan is at risk from other partners not delivering, from changes in the external environment including other higher levels of government making changes that worsen conditions for the target groups.  An example of an external risk would be where refugee status is changed so that social security benefits, the right to work or the right to remain in the country are weakened.  This would be a national change that would impact negatively on the position of refugees in a local community

It is possible to identify three types of risk

- Internal risks that you can control (e.g.design, management systems, performance)

- External risks others control (e.g. national legislation)

- External risks no one controls (e.g. natural disasters)

Table 10 Connecting the Assumptions to the Objectives, outputs and activities

| Intervention logic | Indicators | Means of verification | Assumptions |
| --- | --- | --- | --- |
| Overall goal: Reducing social exclusion among refugees and ethnic minorities |  |  |  |
| Action Plan Objective: To raise the income levels of refugees by increasing their employability and helping them start enterprises |  |  | Refugee status is not changed by the government – refugees are able to work and claim benefits and tax credits |
| Outputs: improved language skills, vocational skills, job placements, |  |  | Partners are able to resource activities and deliver |
| Activities language classes, training programmes, enterprise advice, incubation centre focused on refugee community |  |  | Refugees can be recruited on to courses and programmes |

#### Key questions to uncover the assumptions

If the partnership successfully delivers all of the activities what are the assumptions about external risks that need to be made if the outputs are to be delivered?

If the partnership successfully delivers all of the outputs what assumptions about external risks need to be made if the objective is to be delivered?

Risk management

Identifying the assumptions on which the action plan depends is a passive exercise. The next step is to identify whether some of these risks can be managed.  In risk management there are three ways of handling risk:

- Risks are transferred – this can be done by forms of insurance – so that another agency bears the risk (insuring parties against rain is a common way of dealing with bad weather in the UK)

- Risks are tolerated - if it is difficult to do anything about the risk, then it may be best to take no action – especially if the cost of action is disproportionate

- Risks are treated - usually the intention is to contain the risk at an appropriate level.

### Step 8 Bringing it all together and achieving coherence by using an adapted logical framework

Purpose: to ensure that the action plan is coherent – i.e. that the actions will lead to the outputs, the outputs will lead to the objectives and the objectives support the goal

Techniques:  This can be done either as a technical exercise or as a participative exercise with the stakeholders.

The final act is to assemble all the parts that you have been working on above and put them together in a single matrix, which is called the Logical framework.

The table below shows a Logical framework or log frame that has been adapted for use with an action plan containing a number of activities rather than for a single project.  Log frames are helpful in developing action plans that are coherent with their objectives.  However, the traditional approach can be daunting for a group that is not trained in their use.

If you have gone through all the steps above then you can combine all of it into a single log frame that looks like the one in table 11 below.

Table 11 Adapted version of Logical framework table for LAPS RAPS inclusion

| Intervention logic | Indicators | Means of verification | Assumptions |
| --- | --- | --- | --- |
| Overall goal: Superior strategic goal for the action plan (based on one of the five themes) |  |  |  |
| Action Plan Objective: The changed situation which the action plan is trying to bring about | How to recognise that the action plan objective has been achieved | Sources of information to show progress towards objective | Matters outside the action plan which must happen if the objective is to be achieved |
| Outputs: Products services and other deliverables generated by the action plan partnership | Major characteristics of the outputs | Sources of information and methods used to show delivery of outputs | Matters outside the action plan which must happen if the Outputs are to achieved |

| Title of activities to achieve the outputs | Lead partner | Brief Description of activity | Intended outputs | Target Number of beneficiaries | Timescale start and end | Resources |
| --- | --- | --- | --- | --- | --- | --- |

# Structuring the LAP/RAP Inclusion Report

The work that you have done to reach this stage can now be brought together in a single document.

We suggest that the document has three sections

- The Position or Context:

- The situation of the target groups and the problems that the groups face.

- The main trends and challenges

- Mapping of existing policy

- What works and what does not work

- The Governance:

- How the consultation was carried out,

- The stakeholder analysis

- How the vertical and horizontal stakeholder inputs to the partnership will be organised.

- How the programme will be monitored and evaluated

- The proposals for action:

- The goal, objectives, outputs and activities that make up the action plan together with the indicators and assumptions. This can be presented using the logical framework with a narrative to explain the details.

4.   Annexes:  additional data, examples of good practice from elsewhere

If your group has gone through the 9 steps thoroughly much of this content will already be written and can simply be brought together from existing material.

# Annex 1.  City and sub City indicators from the Urban audit

|  | CITY |  | QUINTILES Comparison with UA cities |  | LUZ |
| --- | --- | --- | --- | --- | --- |
|  | Low |  | High |  |  |  |
| INDICATORS | YEAR | SCORE | 5th | 4th | 3rd | 2nd | 1st | CASES |  | YEAR | SCORE | Ratio City:LUZ |
| DEMOGRAPHY |  |  |  |  |  |  |  |  |  |  |  |  |
| Total resident population | 2001 | 123,062 |  |  |  |  |  | 260 |  | 2001 | 311,479 | 1:2.53 |
| Total annual population change over 5 yrs. | 1996 | 0% |  |  |  |  |  | 210 |  | 1996 | 1% | 1:68.31 |
| EU nationals as a percentage of total population | 2001 | 3% |  |  |  |  |  | 233 |  | 2001 | 3% | 1:1.09 |
| Non-EU nationals as a percentage of total population | 2001 | 4% |  |  |  |  |  | 233 |  | 2001 | 3% | 1:0.77 |
| Average size of households | 2001 | 2.88 |  |  |  |  |  | 260 |  | 2001 | 3.04 | 1:1.06 |
| Percentage of households that are 1-person households | 2001 | 26% |  |  |  |  |  | 248 |  | 2001 | 20% | 1:0.80 |
| Percentage of households that are lone-parent households | 2001 | 14% |  |  |  |  |  | 235 |  | 2001 | 12% | 1:0.86 |
| SOCIAL ASPECTS |  |  |  |  |  |  |  |  |  |  |  |  |
| Average price per m2 for an apartment |  |  |  |  |  |  |  |  |  |  |  |  |
| Average price per m2 for a house |  |  |  |  |  |  |  |  |  |  |  |  |
| Percentage of households living in owned dwellings | 2001 | 63% |  |  |  |  |  | 251 |  | 2001 | 74% | 1:1.18 |
| Percentage of households living in social housing | 2001 | 14% |  |  |  |  |  | 185 |  | 2001 | 8% | 1:0.59 |
| Average living area in m2 per person |  |  |  |  |  |  |  |  |  |  |  |  |
| Life expectancy at birth for males and females |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of recorded crimes per 1,000 population |  |  |  |  |  |  |  |  |  |  |  |  |
| ECONOMIC ASPECTS |  |  |  |  |  |  |  |  |  |  |  |  |
| Unemployment rate | 2001 | 9% |  |  |  |  |  | 241 |  | 2001 | 6% | 1:0.72 |
| Unemployment rate - female | 2001 | 7% |  |  |  |  |  | 240 |  | 2001 | 5% | 1:0.76 |
| Employment rate | 2001 | 58% |  |  |  |  |  | 219 |  |  |  |  |
| Activity rate | 2001 | 58% |  |  |  |  |  | 237 |  | 2001 | 62% | 1:1.08 |
| GDP per head (€) | 2001 | €31,496 |  |  |  |  |  | 161 |  | 2001 | €31,496 | 1:1 |
| Median disposable annual household income(€) |  |  |  |  |  |  |  |  |  |  |  |  |
| Percentage of households receiving less than half of the national average household income |  |  |  |  |  |  |  |  |  |  |  |  |
| CIVIC INVOLVEMENT |  |  |  |  |  |  |  |  |  |  |  |  |
| Percentage of registered electorate voting in city elections | 2001 | 46% |  |  |  |  |  | 198 |  |  |  |  |
| TRAINING AND EDUCATION |  |  |  |  |  |  |  |  |  |  |  |  |
| No. of children aged 0-4 in day care per 1,000 children 0-4 |  |  |  |  |  |  |  |  |  |  |  |  |
| % of resident population with secondary education | 2001 | 23% |  |  |  |  |  | 206 |  | 2001 | 23% | 1:1.02 |
| % of resident population with tertiary education | 2001 | 13% |  |  |  |  |  | 206 |  | 2001 | 13% | 1:0.99 |
| ENVIRONMENT |  |  |  |  |  |  |  |  |  |  |  |  |
| Summer Smog: No. of days ozone (O3) exceeds 120µg/m3 | 2001 | 0 |  |  |  |  |  | 171 |  |  |  |  |
| Number of days PM10 concentrations exceed 50 µg/m3 | 2001 | 15 |  |  |  |  |  | 137 |  |  |  |  |
| Amount of solid waste collected (domestic and commercial) - tonnes per capita per annum |  |  |  |  |  |  |  |  |  |  |  |  |
| Percentage of solid waste processed by landfill |  |  |  |  |  |  |  |  |  |  |  |  |
| Green space to which the public has access (m2 per capita) |  |  |  |  |  |  |  |  |  |  |  |  |
| Population density (residents per km2) |  |  |  |  |  |  |  |  |  |  |  |  |
| TRANSPORT AND TRAVEL |  |  |  |  |  |  |  |  |  |  |  |  |
| Percentage of journeys to work by car | 2001 | 59% |  |  |  |  |  | 129 |  | 2001 | 69% | 1:1.17 |
| Average time of journey to work (mins.) | 2001 | 20 |  |  |  |  |  | 128 |  | 2001 | 22 | 1:1.10 |

SUB CITY LEVEL

13 SUB-CITY DISTRICTS Average Population: 9466 Comparison of Sub-City Districts INDICATORS YEAR LOWEST CITY SCORE HIGHEST RATIO Lowest:Highest DEMOGRAPHY Percentage of total population aged 0-4 2001 3% 6% 9% 1:2.58 Average size of households 2001 2.53 2.88 3.26 1:1.29 Percentage of households that are 1-person households 2001 17% 26% 36% 1:2.20 Percentage of households that are lone-parent households 2001 7% 14% 26% 1:3.77 Percentage of households that are lone-pensioner households 2001 6% 10% 15% 1:2.63 SOCIAL ASPECTS Proportion of dwellings lacking basic amenities 2001 0% 0% 0% ECONOMIC ASPECTS Unemployment rate 2001 5% 9% 14% 1:3.17 Percentage of unemployed who are under age 25 2001 19% 31% 37% 1:1.99 TRAINING AND EDUCATION % of resident population with only primary education 2001 9% 15% 24% 1:2.73 % of resident population with secondary education 2001 14% 23% 31% 1:2.18 % of resident population with tertiary education 2001 6% 13% 29% 1:4.75 ENVIRONMENT Population density (residents per km2)

# Footnotes

Source European Anti Poverty Network website

DG Employment and social affairs website on social inclusion can be found at EUROPA - Employment and Social Affairs - Social Inclusion

available in French or Portuguese

Planning for real is a neighbourhood planning approach developed by Tony Gibson that uses a base map and model of the neighbourhood to encourage residents and planners to share ideas and views about how the local area needs to change.  It can be adapted to other policy issues such as community safety.

Income quintile ratio is defined as the the ratio of total income received by the 20% of the population with the highest income (top quintile) to that received by the 20% of the population with the lowest income (lowest quintile).

this is calculated  using the Gini coefficient which is a measure of inequality of a distribution, defined as the ratio of area between the Lorenz curve of the distribution and the curve of the uniform distribution, to the area under the uniform distribution. The coefficient is a  number between 0 and 1, where 0 corresponds to perfect equality (e.g. everyone has the same income) and 1 corresponds to perfect inequality (e.g. one person has all the income, and everyone else has zero income). It was developed by the Italian statistician Corrado Gini and published in his 1912 paper "Variabilità e mutabilità".

# Text boxes

Local authority lead  or other lead agency  LAP

Horizontal partners

Other departments of local authority, other agencies

Private sector and NGOs

Poor and socially excluded groups

Funders and Policy Makers