Belfast

Budapest

Charleroi

Coventry

Dublin

Liverpool

Pezinok

Toledo

Toulouse

Observer

Timisoara

With the

support of

QEC – ERAN

II Steering Meeting – Budapest 28 September 2006

ACTION PLAN – AGREED ACTIONS

| ITEM | ACTION | WHO | WHEN |
| --- | --- | --- | --- |
| Presage and financial report | Preparing simplified guidelines for using Presage Checking certifying bodies Sending sample of filled timesheet Sending TMT excel file with the list of all expenditures Starting filling Presage with expenditures | TMT TMT + all partners TMT TMT + all partners | Deadlines 5 Oct 06 end October 5 Oct 06 15 Nov. 06 |
| Cofinancing | Send to LP the first tranches of 18.300 EUR confinancing | ALL | 15 Nov. 06 |
| Website | Partner Profiles Key Actors Profiles Contacts for Urb – Health Platform | ALL ALL ALL (minum 5 contacts)+TMT | 15-12- 06 |
| 3st Peer Review Workshop (PREW 3) Sub-Theme : Women and Health | Choose delegates for 1st Peer Review Workshop (PREW 3) and send names to TMT for booking flights Organisation with co – hosting Partner Conference call for planning event Programme Logistic Experts input | ALL | 15 – 01 – 07 |
|  |  | TMT + Liverpool TMT + ALL TMT + Liverpool TMT + PPs to identify partners | From Dec 06 to Feb 07 LIVERPOOL - UK 1st – 3 March 2007 |
| 3rd Steering Group Meeting (SGM 3) + 4th Peer Review Workshop (PREW 4) Sub-theme: Housing and Health |  | TMT + Torino | TORINO - IT |
| Newletter | sending TMT articles, refrences, links, etc preparing the fourth issue : | ALL TMT – Editor & webmaster | 15 Nov 06 end of November 06 |
| Local Mapping | Preparing templates and send to all PPs Filling the template with relevant information | Tommy and TMT ALL | Mid October 06 Mid December 06 |

II Steering Meeting – Budapest 28 September 2006

List of Participants

| Name | Organisation |
| --- | --- |
| Caroline Bloomfield | North and West Belfast Health Action Zone |
| Zsuzsa Kravalic | Studio Metropolitana - HUNGARY |
| Marie Line - Poucet | CPAS – Charleroi - BELGIUM |
| Luisa Avedano Mary Ritrovato Marco Santangelo | City of Torino - ITALY |
| Alan Bennet | Westmidlands – Coventry - UK |
| Elena Globanova | Regional Development Agency – Pezinok - SLOVAKIA |
| Pilar Vigil Marie Claude Remesy | City of Toulouse - FRANCE |
| Helen Bromley | Hearth of Mersey Liverpool - UK |
| Pauline Geoghegan | URBACT expert attached to the Secretariat |
| Aurelio Dugoni Isabella Haaf | QeC-ERAN – BELGIUM |