GENDERWISE:

The role of men as agents of change in reconciling work and family life.

Ref. N°: Grant agreement VS/2005/0338

Accounting No: SI2.414498

1st Steering Group Meeting

Bruxelles, 9-10 january 2006

Agreed actions

ACTION PLAN – AGREED ACTIONS

| ITEM | ACTION | WHO | WHEN |
| --- | --- | --- | --- |
| Website | Partner profile | ALL | 27.01.2006 |
|  | Steering Group profile | ALL |  |
| Local Action Groups (LAGs) | Identify members and send list to QeC-ERAN | ALL | 10.03.2006 |
|  | Complete profiles | ALL |  |
|  | First Local Meeting | ALL |  |
|  | Choose delegates for 1st Peer Review Workshop (PREW 1) | ALL |  |
| 1st Peer Review Workshop (PREW 1) Sub-theme: Socialisation and education | Conference call for planning event | Hosting partner (Barcelone) + QeC-ERAN | 17-20 May 2006, Barcelone |
| Local Mapping | Produce a local report of local actions | ALL | 28.04.2006 |
| Interim report | Submit mapping report | ALL | 28.04.2006 |
|  | LAG report |  |  |
| 2nd Steering Group Meeting (SGM 2) |  | QeC-ERAN | 18-19 June 2006, Bruxelles |
| 3rd Steering Group Meeting (SGM 3) + 2nd Peer Review Workshop (PREW 2) Sub-theme: Gender equality in the workplace | Conference call for planning event | Hosting partner (Enna) + QeC-ERAN | 27 September – 1 October 2006, Enna |
| 3rd Peer Review Workshop (PREW 3) |  | QeC-ERAN | 29 November – 2 December 2006, Bruxelles |
| 4th Steering Group Meeting (SGM 4) |  | QeC-ERAN | 1-2 February 2007, Bruxelles |

Participants

| Name | Organisation | Country |
| --- | --- | --- |
| Haroon Saad | QeC-ERAN | BELGIUM |
| Aurelio Dugoni | QeC-ERAN | BELGIUM |
| Andrea Giordano | QeC-ERAN | BELGIUM |
| Minna Riutta | QeC-ERAN | BELGIUM |
| Nasseur Oussedik | ACCEDO | FRANCE |
| Antonia Nemes | JOL-LET Foundation | HUNGARY |
| Katalin Kevehazi | JOL-LET Foundation | HUNGARY |
| Judit Takács | MTA SZKI | HUNGARY |
| Michele Sabatino | CESIS | ITALY |
| Stefania Gavin | The Gate | ITALY |
| Jennifer Rieskin | Stadsdeel Zuidoost – Amsterdam | NETHERLANDS |
| Andrea Oel-Brettschneider | RDA SP | SLOVAKIA |
| Begoña Ballesteros Sánchez | AMESAL | SPAIN |
| Lidia Garcia Alises | FEMPCLM | SPAIN |
| Juan Pedregosa | ITD | SPAIN |
| Sarbjit Duggal | Shantona Women's centre | UK |