European Residents in Regeneration Network

Ref. n° : 2006 – 2739/ 001- 001 PPC PPC

1st Steering Group Meeting

3-4 December 2006, Brussels

LIST OF ATTENDANTS

| NAME | ORGANISATION |
| --- | --- |
| J.W.E. van de Poel | Charlois District of Rotterdam, THE NETHERLANDS |
| Eric Dosimont | CPAS Charleroi, BELGIUM |
| Michael Johnson | Olmec, UK |
| Adriana Goni Mazzitelli | Rete Monti – Uni Roma 3, ITALY |
| Alessandra Felici | Rete Monti – Uni Roma 3, ITALY |
| Vicky Triga | University of Thessaloniki, GREECE |
| Fernando Méndez | University of Thessaloniki, GREECE |
| Juan Pedregosa | CEPS, SPAIN |
| Luisa Avedano | Citta`di Torino, ITALY |
| Bruno Lestienne | CdQ de l’Hommelet, FRANCE |
| Carlos Ribeiro | Universidade do Porto, PORTUGAL |
| Isabella Haaf | QeC-ERAN |
| Haroon Saad | QeC-ERAN |
| Annachiara Pecchini | QeC-ERAN |
| Carl García | QeC-ERAN |
| Tamara Hodas García | QeC-ERAN |

AGREED ACTION PLAN

| DECEMBER | ACTIONS | WHO | By WHEN |
| --- | --- | --- | --- |
|  | 1. SGM: notes of meeting + agreed action plan | QeC-ERAN | 11/12 |
|  | 2.Send questionnaire | QeC-ERAN | 11/12 |
|  | 3.Send themes | QeC-ERAN | 11/12 |
|  | 4.Send financial and administration forms | QeC-ERAN | 11/12 |
|  | 5.Contract for Online Platform | QeC-ERAN + University of Thessaloniki | 5/12 (agreed) |
|  | 6.Send back completed “Staff declaration form” | ALL | 20/12 |
|  | 7.Send expenses claim form | ALL | 20/12 |
|  | 8.List of names of LRFs members | ALL | 20/12 |
|  | 9.Send flyer for Workshop | ALL | 11/12 |
| JANUARY | ACTIONS | WHO | WHEN |
|  | 1. Send Profiles of residents | ALL | End of month |
|  | 2. Send questionnaires filled in | ALL | End of month |
|  | 3.Send themes back to QeC | ALL | End of month |
|  | 4.Platform VERSION 1 | University of Thessaloniki | End of month |
|  | 5.Identify attendants to Workshop (send ID copy to book flight) | ALL | End of month |
| FEBRUARY | ACTIONS | WHO | WHEN |
|  | 1.Draft Programme of Workshop | QeC-ERAN | 12/2 |
|  | 2.Feedback on Online Platform version 1 | ALL | 12/2 |
|  | 3.All profiles completed | ALL | 12/2 |
|  | 4.Information Forum: -Local Forums -EU Forum | ALL + QeC-ERAN | 26/2 |
|  | 5.Feedback on Online Platform VERSION 2 | ALL | End of the month |
| MARCH | ACTIONS | WHO | WHEN |
|  | 1.Final programme for Workshop | QeC-ERAN | 16/3 |
|  | 2.Result of Skills & Training Audit | QeC-ERAN | 26/3 (at workshop) |
|  | 3.VERSION 3 of Platform | University of Thessaloniki | 26/3 (at workshop) |
|  | 4.WORKSHOP + 2nd SGM | ALL | 26-29/3 |
| APRIL | ACTIONS | WHO | WHEN |
|  | 1.Outcomes of workshop on platform | QeC-ERAN | 16/4 |
|  | 2.Update info on platform: -Local Forums -EU Forum | ALL + QeC-ERAN | Ongoing |
|  | 3.First horizontal exchange | ALL | Starting end of April; Finishing end of May |
| JUNE/JULY | ACTIONS | WHO | WHEN |
|  | 1.3rd SGM | ALL | 24-25/6 |
|  | 2.Forward strategy | ALL | 25/6 |
|  | 3.Financial Closure (all timesheets and claim forms sent to QeC-ERAN) | ALL | Mid-July |
| SEPTEMBER | ACTIONS | WHO | WHEN |
|  | 1.Final Report | University of Thessaloniki | End of September |