LAPs & RAPs

1st Steering Group Meeting

Bruxelles, 7-8 November 2005

Agreed actions

ACTION PLAN – AGREED ACTIONS

| ITEM | ACTION | WHO | WHEN |
| --- | --- | --- | --- |
| Local coordination | Proposal from each partner for local coordination: Budget Staff contract (if temporary employee) External contract (to someone appointed ad hoc) | All | 15/11 |
|  | Send pro-forma for budget and staff contract | Venice | 09/11 |
| Co-financing | Submit proposal to Venice | All | 15/11 |
| Steering Group Meetings | Who is representative plus substitute (format sent by Venice) | All | 15/11 |
| Web site | Pro-forma for: Partner organisations Profiles for LDG members | QeC | 15/11 |
| LDG | Establish LDG (at least 50%=6 members) | All | 05/12 |
|  | Fill-in profiles | All | 05/12 |
| PREW 1 (PRAGUE: 8-9-10-11 February 2006) | Participants | All | 12/12 |
|  | Experts suggested | All | 12/12 |
|  | Conference call | Venice + QeC+ hosting partner |  |
|  | Plane tickets | All | Before Christmas |
|  | Information pack for participants | Venice | 2 weeks before PREW |
|  | Draft programme | QeC | 2nd week of January 2006 |
|  | Orientation paper | QeC | 2nd week of January 2006 |
| Local / Regional Action Plans | Agree priority themes | All | 27/01/2006 |
|  | Local mapping | All | March / May 2006 |
| 6 monthly reports | Pro-forma report | Venice | 01/02/2006 |
|  | Activity report | All | 01/03/2006 |
| PREW 2 + SGM 2 | in ROME: 16-17-18-19 May 2006 |
| SKYPE | www.skype.com | All | 15/12/2005 |

List of participants

|  | City | Name | Organisation |
| --- | --- | --- | --- |
| 1 | SLOVENIA | Suzi Kvas | Javni Zavod Socio |
| 2 | CZECH REPUBLIC | Jitka Zukalová | Ministry of Labour and Social Affairs |
| 3 | PORTUGAL | Alexandra Amorim | Institute of Social Security |
| 4 | GREECE | Ioanna Svirkou | Municipality of Thessaloniki |
| 5 | GREECE | Natassa Paraskeva | Association for the Development of west Athens ASDA |
| 6 | SPAIN | Jose Luis Rubio | Giunta de Comunidad de Castilla La Mancha |
| 7 | SPAIN | Juan Gualda | Giunta de Comunidad de Castilla La Mancha |
| 8 | ITALY | Diego Teloni | Fondazione Brodolini |
| 9 | ITALY | Giuseppe Panebianco | City of Rome |
| 10 | ITALY | Michele Testolina | City of Venice |
| 11 | ITALY | Andrea Del Mercato | City of Venice |
| 12 | ITALY | Tiziana Alvisi | City of Venice |
| 13 | ITALY | Serafina Scerra | City of Crotone |
| 14 | BELGIUM | Andrea Giordano | QeC-ERAN |
| 15 | BELGIUM | Haroon Saad | QeC-ERAN |