Outstanding actions as of November 04, as agreed during the 3rd SGM:

| Outstanding Actions | 3rd December 1st week of December 2nd week of December 2 weeks after reception of all reports | List of participants for 4th PREW communicated to QeC & Host Participants and coordinators profiles (incl. photo) sent to QMT Profiles inserted on QeC website Travel vouchers and invoices for 2nd and 3rd SGM & 2nd and 3rd PREW sent to QeC PREW hosts inform QeC of all expenses incurred during PREW and provide original invoices Torino PREW report finalised with input from AMECOOP Belfast PREW reports sent to Belfast Provide QeC with original signed coordination contracts QMT determines possible budget flexibility for 4th PREW Belfast PREW report finalised with input from all partners | Coordinators Coordinators QMT Coordinators Coordinators Host Coordinators Coordinators QMT PREW Host |
| --- | --- | --- | --- |
| New Action Agreed | throughout Jan. & Feb. 05 | QMT and Partners agree on 3 participants per partner who will be interviewed cc. ways to promote women participation in decision making | QMT & coordinators |

| November 04 | 17th-21st 29th | 3rd SGM and PREW in Toledo participants give Toledo PREW reports to local coordinators | local participants (and coordinators) |
| --- | --- | --- | --- |
| December 04 | 2nd 3rd 6th 6th 6th 6th 6th 6th 6th 10th 13th 17th reception of last report + 2 weeks | Financial cash flow agreements: 1st monitoring table List of participants for 4th PREW communicated to 4th PREW Host QMT and partners decide which partners will be interviewed local coordinators send collated reports to Toledo all participants and coordinators profiles (incl. photo) have been sent to QMT PREW hosts have informed QeC of all expenses incurred at PREW & provided original invoices Travel vouchers for 2nd and 3rd SGM as well as 2nd and 3rd PREW have all been sent to QeC Torino PREW report finalised with input from AMECOOP All Belfast PREW reports sent to Belfast Participants profiles available on QeC website Provide QeC with original signed coordination contracts QMT determines budget flexibility for 4th PREW Final report Belfast | QMT Coordinators QMT and Partners Coordinators Coordinators Hosts Coordinators Hosts Coordinators QMT Coordinators QMT Host |
| January 05 | 2nd week Jan. 21st 27th –29th | Select participants for interviews Final Report Toledo 4th Final PREW in Northamptonshire start interviews of selected participants | QMT & participants Host QMT & participants |
| February 05 | All month 1st week 15th | Interviews of selected participants for case-studies participants give PREW reports to coordinators coordinators send collated reports to Northampton 4th SG in Brussels | QMT & participants participants and coordinators coordinators |
| March 05 | All month 4-5th | Interviews of selected participants for case-studies - 4th SGM in Brussels Project ends | QMT & participants |

Timetable and Action plan from 3rd SGM on 17 November 04 until end of project