Timetable January 2004 – March 2005

| Month | Dates | Activity | Activity |
| --- | --- | --- | --- |
| January |  | Website Finalising contract Setting up QMT Arranging Steering Group Meeting (SG) | QMT |
| February | 5-8. 13. | 1st SG Meeting in Brussels Agree with EC on changes in : SG, local coordination, interpretation, co-financing Give partners “contract” details for local coordination Information/recruitment pack for participants & application/ profile forms Recruit local coordinators Begin recruitment of local participants Each Partner pays 50% of co-financing ( Receives 50% of local coordination cost | QMT QMT QMT Partners Partners QMT & Partners |
| March | 12. | First 4 participants Local participants group meeting Personal Profiles of Partners Agreed format for peer-review Identify participants Book Flights & Insurance Book hotels Establish website | Partners Partners Partners QMT Partners QMT Host QMT |
| April | 8. | Second 4 participants Draft & Final Programme Venue & Catering & Interpretation | Partners Host & QMT Partner |

| May | 27-30. | Joining Pack Mid-term report to EC 1st Peer- review Exchange Workshop (PREW) in Turin on “Family and Social Inclusion” | QMT & Partners |
| --- | --- | --- | --- |
| June |  | Each Partner pays 2nd installment of co-financing Peer-review reports x 6 | Partner Local coordinator & participants |
| July | 1-4. | Collated report 2nd SG in Brussels Each Partner receives 2nd installment of local coordination cost | Host QMT |
| August |  | H o l i d a y |  |
| September | 23-26. | 2nd PREW in Belfast on “Women and Participation” |  |
| October | 14-17. | 3rd PREW in Toledo on “Women and Labour Market” |  |
| November | 18-21. | 4th Final PREW & 3. SG in Northamptonshire and Birmingham |  |
| December |  |  |  |
| January |  |  |  |
| February |  | 4th SG in Brussels |  |
| March |  | Project ends |  |