Getting Engaged: Women in Local Development

Ref. N°: Grant agreement VS/2006/0430

Accounting No: SI2.443736

3rd Steering Group Meeting

Rome, 17 October 2007

Action Plan

As agreed at the 2nd SGM

| Date | Action | Who | Deadline |
| --- | --- | --- | --- |
| January 2007 | Partner profile | All partners | 31/01/2007 |
|  | Local coordinator(s) + staff declaration | All partners | 31/01/2007 |
|  | Expenses claim SGM1 | All partners | 31/01/2007 |
| February 2007 | Local coordination Group completed + staff declaration | All partners | 09/02/2007 |
|  | Establish Local Action Group (LAG) | All partners | 28/02/2007 |
|  | 1st LAG meeting | All partners | 28/02/2007 |
|  | Start PREW1 planning | QeC-ERAN + host partner | 28/02/2007 |
| March 2007 | LAG profiles +professional profile for each LAG participant including local coordinator | All partners | 31/03/2007 |
|  | Local Action Group completed | All partners | 31/03/2007 |
|  | Submit timesheets (12/2006 - 03/2007) | All partners | 31/03/2007 |
| April 2007 | Begin local mapping | All partners | 30/04/2007 |
|  | 2nd LAG meeting | All partners | 30/04/2007 |
| May 2007 | POZNAN (Poland): SGM2 (16 May – pm) + PREW1 (17+18 May) | QeC-ERAN + host partner | 16+17+18/ May2007 |
| June 2007 | Submit local mapping report + linked action plan | All partners | 29/06/07 |
|  | 3rd LAG meeting | All partners | 29/06/07 |
|  | Submit timesheets (4/2007 - 6/2007) | All partners | 29/06/07 |
|  | Activity report from each LAG:to be included in the Interim report for COM | All partners | 29/06/07 |
| July 2007 | Interim report for Commission | QeC-ERAN | 15/07/07 |
| September 2007 | 4th LAG meeting | All partners | 28/09/07 |
| October 2007 | ROMA (Italy): SGM3 (17 October – pm) + PREW2 (18+19 October) | QeC-ERAN + host partner | 17-18-19/10/07 |
|  | Bring timesheets (7/2007 - 9/2007) | All partners | 31/10/07 |
| November 2007 | 5th LAG meeting | All partners | 30/11/07 |
| December 2007 | BRUXELLES (Belgium): SGM4 (12 December – pm) + PREW3 (13+14 December) | QeC-ERAN | 13-14/12/07 |
| January 2008 | Local dissemination event | All partners | 31/01/08 |
| February 2008 | Submit timesheets (10/2007 - 2/2008) | All partners | 28/02/08 |